## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BASUDEBPUR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2023-2024 | 2335/BQA | 14/08/2023 | 06/12/2024 | KHAN ENTERPRISE | 529.02 | 36.44 | 6.89 | 2
2 | BANKURA | Sonamukhi | Bankura Division | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 125.93 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Basudebpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000030/2023-2024 | 657/BMD | 17/04/2023 | 14/10/2023 | RAJIB COMPANY | 40.25 | 19.17 | 47.61 | 48
Total | [13 empty] | 695.21 | 55.61 | 8