## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Prakash Zone-B Water Supply Scheme | SM/16945 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PRAKASH ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000334/2023-2024 | 2004/BQA | 19/07/2023 | 14/04/2024 | S.N POLYMERS PVT LTD | 125.9 | 6.81 | 5.41 | 5
2 | BANKURA |  | Bankura Mechanical | Augmentation of Prakash Zone-B Water Supply Scheme | SM/16945 | Augmentation | Augmentation of Prakash Zone-B Water Supply Scheme |  |  | BILL/00168/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Prakash Zone-B Water Supply Scheme | SM/16945 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Prakash (Zone-B) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000388/2023-2024 | 1710/BMD | 28/07/2023 | 26/09/2023 | KASHINATH DEY | 20.9 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Prakash Zone-B Water Supply Scheme | SM/16945 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Prakash Zone -B and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001099/2023-2024 | 3074/BMD | 12/03/2024 | 10/07/2024 | S. G. TECHNICAL SERVICE | 15.72 | 0 | 0 | 0
Total | [13 empty] | 164.02 | 6.81 | 4.15