## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16959 | Augmentation | Augmentation of Godardihi (Zone - E) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000510/2023-2024 | 2361/BQA | 14/08/2023 | 10/05/2024 | MUNMUN UPADHYAY | 177.79 | 19.42 | 10.92 | 20
2 | BANKURA |  | Bankura Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16959 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 2732/BQA | 03/10/2023 |  | Resource Division | 1.23 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16959 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000228/2023-2024 | 193/BQA | 22/01/2024 |  | Resource Division | 1.23 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16959 | Augmentation | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00140/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16959 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Godardihi ( Zone-E) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000302/2023-2024 | 1405/BMD | 18/07/2023 | 16/09/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 81.77 | 30.92 | 37.81 | 74
Total | [13 empty] | 263.53 | 50.33 | 19.1