## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Balance allied works of augmentation works for Harialgara ( Zone-O ) under Bankura - I, II & Barjora Block water supply scheme. | Assistant Engineer |  | ORD/000186/2024-2025 | 1815/BQA | 11/07/2024 | 07/04/2025 | SUBHADIP KOLE | 245 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Augmentation of HARIALGORA (Zone - O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000384/2023-2024 | 2044/BQA | 24/07/2023 | 19/04/2024 | PRADIP RAJAK | 310.94 | 97.35 | 31.31 | 53
3 | BANKURA |  | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Harialgara (Zone- O) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001197/2023-2024 | 450/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 3.08 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1736/BQA | 05/07/2024 |  | Resource Division | 16.9 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 2732/BQA | 03/10/2023 |  | Resource Division | 4.42 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000240/2023-2024 | 193/BQA | 22/01/2024 |  | Resource Division | 4.42 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00146/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/01613/2023-2024 | BP-2023-24-138 | 07/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16967 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Harialgara (Zone O) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000517/2023-2024 | 1882/BMD | 17/08/2023 | 15/12/2023 | MAHADEV ENTERPRISE | 81.83 | 10.86 | 13.27 | 42
Total | [13 empty] | 669.51 | 108.21 | 16.16