## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17242 | Augmentation | Augmentation of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 1410/BQA | 08/06/2023 | 04/03/2024 | SUBHENDU SEKHAR GORAI | 122.67 | 30.1 | 24.54 | 50
2 | BANKURA |  | Bankura Division | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17242 | Augmentation | Soil Investigation work for construction of OHR (500 CUM CAPACITY) under Augmentation works for KUSTORA (Zone- W2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000892/2023-2024 | 3043/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.56 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17242 | Augmentation | Support service for design of pipe network under Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001207/2023-2024 | 460/BQA | 08/02/2024 | 09/03/2024 | ROY CHOWDHURY ASSOCIATES | 4 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17242 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 2732/BQA | 03/10/2023 |  | Resource Division | 0.36 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17242 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000277/2023-2024 | 193/BQA | 22/01/2024 |  | Resource Division | 0.36 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17242 | Augmentation | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00152/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17242 | Augmentation | Acceptance cum Formal work order for the work of Supply, delivery and installation of online Boosting pumping machineries and other electromechanical accessories at OHR site of Kustora (Zone-W) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000273/2024-2025 | 778/BMD | 20/08/2024 | 18/12/2024 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 29.28 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17242 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kustora (Zone-W) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000318/2023-2024 | 1467/BMD | 18/07/2023 | 16/09/2023 | RABINDRA NATH KHAN | 81.75 | 0 | 0 | 63
Total | [13 empty] | 240.47 | 30.1 | 12.52