## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF MORAR ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 2037/BQA | 24/07/2023 | 11/10/2025 | M/S D.PALIT & CO. | 159.64 | 40.7 | 25.49 | 25
2 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Augmentation of Morar Zone-B Water Supply Scheme |  |  | BILL/00165/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HSC pumping machineries with allied work for Augmentation of Marar Zone-B and adjoining mouzas water supply scheme (BRGF Ph I) at CWR site Gopalpur , Block Bishnupur under Jal Jeevan Mission programme under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000267/2024-2025 | 775/BMD | 20/08/2024 | 18/12/2024 | M/S NABIN GOPAL SENGUPTA | 44.9 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Marar Zone-B piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000390/2023-2024 | 1711/BMD | 28/07/2023 | 26/09/2023 | M.S. ENTERPRISE | 95.96 | 36.4 | 37.94 | 81
Total | [13 empty] | 302.01 | 77.1 | 25.53