## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Benda water supply scheme | SM/17244 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF BENDA PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000332/2023-2024 | 2002/BQA | 19/07/2023 | 14/04/2024 | S.N POLYMERS PVT LTD | 143.48 | 15.43 | 10.75 | 5
2 | BANKURA |  | Bankura Mechanical | Augmentation of Benda water supply scheme | SM/17244 | Augmentation | Augmentation of Benda water supply scheme |  |  | BILL/00186/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Benda water supply scheme | SM/17244 | Augmentation | Submission of quotation for new service connection at Mouza Ranikhamar of Benda w/s scheme.SM/17244 |  |  | BILL/00538/2024-2025 | BP-2024-25-144 | 25/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.15 | 0 | 0 | null
4 | BANKURA |  | Bankura Mechanical | Augmentation of Benda water supply scheme | SM/17244 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Benda and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000137/2024-2025 | 443/BMD | 27/06/2024 | 25/10/2024 | UNITED TRADERS | 21.56 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Benda water supply scheme | SM/17244 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Benda piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000515/2023-2024 | 1880/BMD | 17/08/2023 | 15/12/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 65.93 | 19.85 | 30.1 | 42
Total | [13 empty] | 235.62 | 35.27 | 14.97