## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Ajodhya Water Supply Scheme | SM/17246 | Augmentation | Nabanda- Joykrishnapur road from 25.800 km to 26.800 km restoration work of road due to laying of pipe lines for Ayodhya piped water supply scheme under JJM project by bankura division PHE Dte. under Bankura Highway Division .P.W.D in the district of Bankura |  |  | BILL/02662/2023-2024 | FHTC/03 | 22/03/2024 |  | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 2.2 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Ajodhya Water Supply Scheme | SM/17246 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AJODHYA PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000389/2023-2024 | 2049/BQA | 24/07/2023 | 19/04/2024 | PRINCE INDUTRIES (INDIA) | 190.71 | 40.14 | 21.05 | 20
3 | BANKURA |  | Bankura Mechanical | Augmentation of Ajodhya Water Supply Scheme | SM/17246 | Augmentation | Quotation as per WBSEDCL procedure -A(2010) on turn key/full deposit basis for new service connection at Mouza Amrel of Ajodhya w/s scheme .SM/17246 |  |  | BILL/00031/2024-2025 | BP-2024-25-14 | 10/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0 | null
4 | BANKURA |  | Bankura Mechanical | Augmentation of Ajodhya Water Supply Scheme | SM/17246 | Augmentation | Quotation as per WBSEDCL Procedure -A(2010) on turn key /full deposit basis for new service connection at Mouza Paikpara of Ajodhya W/S scheme. |  |  | BILL/00112/2024-2025 | BP-2024-25-15 | 10/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.52 | 0 | 0 | null
5 | BANKURA |  | Bankura Mechanical | Augmentation of Ajodhya Water Supply Scheme | SM/17246 | Augmentation | Augmentation of Ajodhya Water Supply Scheme |  |  | BILL/00172/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation of Ajodhya Water Supply Scheme | SM/17246 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Ajodhya piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000456/2023-2024 | 1782/BMD | 01/08/2023 | 29/11/2023 | ABHIJIT MUKHERJEE | 52.17 | 16.42 | 31.46 | 63
7 | BANKURA |  | Bankura Mechanical | Augmentation of Ajodhya Water Supply Scheme | SM/17246 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High Lift pumping machineries and other electromechanical accessories at CWPH for Augmentation of Ajodhya and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001098/2023-2024 | 3073/BMD | 12/03/2024 | 10/07/2024 | TAPAN KUMAR SARKAR | 39.24 | 0 | 0 | 0
Total | [13 empty] | 301 | 56.56 | 18.79