## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Work Order for Supply, Delivery and Stacking of Air Valve of Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000124/2023-2024 | 126/KSD | 25/05/2023 | 09/06/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.94 | 0.94 | 100 | 20
2 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Sinking of 3 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-K (Makhnu) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000791/2022-2023 | 675/BQA | 28/03/2023 | 10/08/2023 | GOUTAM BHATTACHRYYA | 75.44 | 29.37 | 38.93 | 20
3 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Sinking of 2 (Two) Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction of 4 (Four) Nos. Pump Houses with ancillary works in different mouzas of Zone-K (Makhnu) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001154/2023-2024 | 358/BQA | 06/02/2024 | 07/03/2024 | SUBHADIP KOLE | 37.55 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 1.42 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Makhnu (Zone- K) ( boosting at tail end) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000150/2024-2025 | 493/BMD | 09/07/2024 | 06/11/2024 | M/S BIPUL BANERJEE | 49.9 | 0 | 0 | 0
Total | [13 empty] | 165.25 | 30.31 | 18.34