## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Sinking of 2 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 1 No. CWR at OHR site, Construction of 1 No. Pump House at Tubewell site, Laying of pipeline and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2024-2025 | 1521/BQA | 19/06/2024 | 19/07/2024 | SINGHA ENTERPRISE | 51.88 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Laying HDPE pipeline from Arkama OHR site to Rangibari and Amdiha village to Bena G.P. Office to increase pressure at Gopisagar & Rangibari Village in connection with Augmentation of Arkama (Zone-H) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000267/2024-2025 | 2133/BQA | 07/08/2024 | 21/09/2024 | JAGABANDHU MONDAL | 3.93 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Arkama village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/000446/2023-2024 | 254/KSD | 24/08/2023 | 31/08/2023 | M/S SUPRIYA CHATTERJEE | 0.95 | 0.94 | 99.08 | 20
4 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Arkama village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/000448/2023-2024 | 256/KSD | 24/08/2023 | 31/08/2023 | M/S SUPRIYA CHATTERJEE | 0.7 | 0.7 | 99.99 | 20
5 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Sindurpeti village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000450/2023-2024 | 258/KSD | 24/08/2023 | 31/08/2023 | GOURANGA CHATTERJEE | 0.7 | 0.69 | 98.1 | 20
6 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000801/2022-2023 | 726/BQA | 30/03/2023 | 14/05/2023 | UTTAM KUMAR SINHAMAHAPATRA | 48.95 | 37.7 | 77 | 100
7 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Laying HDPE pipeline to increase pressure in Damodarpur Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) of Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001126/2023-2024 | 247/BQA | 25/01/2024 | 24/02/2024 | BIKASH MANDAL | 5.11 | 2.41 | 47.14 | 80
8 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 2.96 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at tail end and CWR site for for Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) under Bankura Mechanical Division, PHE Dte. Block : Khatra , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000169/2024-2025 | 511/BMD | 09/07/2024 | 06/11/2024 | RAJIB COMPANY | 44.01 | 0 | 0 | 0
Total | [13 empty] | 159.2 | 42.44 | 26.66