## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17260 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone- Malian in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000607/2022-2023 | 560/BQA | 17/03/2023 | 01/05/2023 | PARESH CHANDRA LAYEK | 32.12 | 20.93 | 65.17 | 100
2 | BANKURA |  | Bankura Division | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17260 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 1.23 | 0 | 0 | 0
Total | [13 empty] | 33.35 | 20.93 | 62.76