## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 4 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme |  |  | BILL/00195/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme |  |  | BILL/00213/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | New service connection for Gargaria water supply scheme under Bankura Mechanical Division Dte. |  |  | BILL/00383/2024-2025 | BP-2024-25-84 | 11/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0 | null
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | New service connection for Gargaria water supply scheme under Bankura Mechanical Division PHE Dte. |  |  | BILL/00384/2024-2025 | BP-2024-25-87 | 11/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.43 | 0 | 0 | null
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | New 3 phase service connection for site Gargaria Zone A |  |  | BILL/00697/2024-2025 | null | 01/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0 | null
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | New 3 phase service connection for site Gargaria Zone A |  |  | BILL/00698/2024-2025 | null | 01/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.43 | 0 | 0 | null
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HL Pumping machineries with illumination system other electromechanical accessories for Augmentation for Gargariya Zone-A and adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000172/2024-2025 | 514/BMD | 09/07/2024 | 06/11/2024 | S.P. CONSTRUCTION | 78.81 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineries with allied works for Augmentation works for Gargariya Zone B water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000321/2024-2025 | 862/BMD | 29/08/2024 | 27/12/2024 | TAPAN KUMAR SARKAR | 34.3 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Gargariya Zone-A water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer |  | ORD/000573/2023-2024 | 2029/BMD | 01/09/2023 | 30/12/2023 | S.P. CONSTRUCTION | 90.11 | 0 | 0 | 0
Total | [13 empty] | 223.43 | 0 | 0