## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF KARISUNDA PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000391/2023-2024 | 2051/BQA | 24/07/2023 | 19/04/2024 | SIB SANKAR CHOWDHURY | 177.69 | 26.02 | 14.64 | 20
2 | BANKURA |  | Bankura Mechanical | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Augmentation of Karisunda Water Supply Scheme |  |  | BILL/00189/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Augmentation of Karisunda Water Supply Scheme |  |  | BILL/01620/2023-2024 | BP-2023-24-153 | 19/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.19 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Karisunda piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000384/2023-2024 | 1707/BMD | 28/07/2023 | 26/09/2023 | ABHIJIT MUKHERJEE | 61.17 | 20.08 | 32.83 | 66
Total | [13 empty] | 245.56 | 46.1 | 18.77