## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17433 | Augmentation | New service connection for Keshia, Jl-241,plot-72,Kadra (Zone-G) Mini water supply scheme under Bankura Division PHE DTE. |  |  | BILL/00129/2024-2025 | BP-77/2024-25 | 22/05/2024 |  | KHATRA CCC | 0.46 | 0 | 0 | null
2 | BANKURA |  | Bankura Division | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17433 | Augmentation | Laying HDPE pipeline with all allied works of Zone-G (Kadra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000193/2024-2025 | 2134/BQA | 07/08/2024 | 06/10/2024 | TAPAN KUMAR MANDAL | 26.97 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17433 | Augmentation | Construction of Pump House with ancillary works for newly constructed Tubewell site (Location- Kesia High School) of Zone-G (Kadra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000284/2024-2025 | 2177/BQA | 12/08/2024 | 26/09/2024 | SAIMUDDIN MOLLAH | 6.22 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17433 | Augmentation | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-G (Kadra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000802/2022-2023 | 721/BQA | 30/03/2023 | 14/05/2023 | MUNMUN UPADHYAY | 80.93 | 48.98 | 60.52 | 32
5 | BANKURA |  | Bankura Division | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17433 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 2.22 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17433 | Augmentation | Acceptance cum Formal work order for the work of Replacement of Valves on the delivery line at IBS Belboni, for Augmentation work for Khyerkanali ( Zone-J) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000134/2024-2025 | 440/BMD | 27/06/2024 | 25/10/2024 | SARVATAH PROJECTS PRIVATE LIMITED | 42.76 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17433 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Kadra (Zone- G) ( Boosting at Tail end) under Khatra-Hirbandh-Ranibandh Water Supply Scheme piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Khatra , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000168/2024-2025 | 510/BMD | 09/07/2024 | 06/11/2024 | RAJIB COMPANY | 13.22 | 0 | 0 | 0
Total | [13 empty] | 172.77 | 48.98 | 28.35