## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF BETANAL ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000501/2023-2024 | 2351/BQA | 14/08/2023 | 10/05/2024 | SUBHANKAR BANERJEE | 168.53 | 41.87 | 24.84 | 18
2 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Augmentation of Betanal Zone-A Water Supply Scheme |  |  | BILL/00178/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Augmentation of Betanal Zone-A Water Supply Scheme |  |  | BILL/01624/2023-2024 | BP-2023-24-151 | 19/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.77 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Acceptance cum Formal work order for the work of Supply, delivery and Installation of Valves with other electro-mechanical accessories at Betanal CWR pipe line based water supply schemes of Indus under B.M.D, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000272/2024-2025 | 777/BMD | 20/08/2024 | 18/12/2024 | M/S SWAPAN BANERJEE | 12.56 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Betanal Zone-A piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000516/2023-2024 | 1881/BMD | 17/08/2023 | 15/12/2023 | EASTERN INDIA SALES & SERVICE | 48.95 | 5.97 | 12.2 | 45
Total | [13 empty] | 234.32 | 47.84 | 20.42