## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17694 | Augmentation | Augmentation of Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 2346/BQA | 14/08/2023 | 10/05/2024 | SWAPAN KUMAR UPADHYAY | 214.79 | 13.13 | 6.11 | 45
2 | BANKURA |  | Bankura Division | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17694 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Joykrishnapur (Zone- I) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001183/2023-2024 | 435/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 1.85 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17694 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 2732/BQA | 03/10/2023 |  | Resource Division | 2.54 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17694 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000259/2023-2024 | 193/BQA | 22/01/2024 |  | Resource Division | 2.54 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17694 | Augmentation | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00159/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17694 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Joykrishnapur (Zone-I) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000159/2024-2025 | 501/BMD | 09/07/2024 | 06/11/2024 | M/S NABIN GOPAL SENGUPTA | 13.36 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17694 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Joykrisnapur ( Zone-I) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000300/2023-2024 | 1403/BMD | 18/07/2023 | 16/09/2023 | M/S SOMA ENTERPRISES | 81.75 | 14.59 | 17.85 | 35
Total | [13 empty] | 317.82 | 27.72 | 8.72