## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Work Order for Extension of distribution pipeline by UPVC pipe (6Kg/Sq. Cm. Water Pressure, class III) along with allied works at Rakhapara village of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000455/2023-2024 | 263/KSD | 24/08/2023 | 08/09/2023 | S. B. CONSTRUCTION | 0.96 | 0.48 | 49.88 | 95
2 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000608/2022-2023 | 561/BQA | 17/03/2023 | 01/05/2023 | MAHARAJA CONSTRUCTION CO. | 44.9 | 29.05 | 64.7 | 40
3 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 2.34 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) |  |  | BILL/00205/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
Total | [13 empty] | 49.2 | 29.52 | 60.01