## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-B (Tilaboni) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000609/2022-2023 | 566/BQA | 17/03/2023 | 01/05/2023 | M/S SUPRIYA CHATTERJEE | 61.85 | 61.4 | 99.28 | 100
2 | BANKURA |  | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Laying HDPE pipeline, Construction and Commissioning of FHTC (Functional House Hold Tap Connection), Construction of platform with all allied works of Zone-B (Tilabani) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 401/BQA | 07/02/2024 | 23/03/2024 | M/S PARAMESWAR CHOWDHURY | 54.4 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 2.59 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000296/2023-2024 | 738/BQA | 01/03/2024 |  | Resource Division | 25.98 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) |  |  | BILL/00204/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
Total | [13 empty] | 145.81 | 61.4 | 42.11