## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | SM/18036 | Augmentation | Preparation of DPR for Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura under Jal Jeevan Mission (JJM) Project of Bankura Sadar Sub - Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2023-2024 | 1335/BQA | 01/06/2023 | 01/07/2023 | ENVIROTECH SOLUTIONS | 3.48 | 3.46 | 99.47 | 100
2 | BANKURA |  | Bankura Division | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | SM/18036 | Augmentation | Augmentation of Indpur Piped water supply scheme, Block - Bankura - I,under Bankura (Sadar) Sub - Division within Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000529/2023-2024 | 2363/BQA | 14/08/2023 | 10/05/2024 | S. S. S. ENTERPRISES | 463.15 | 0 | 0 | 27
3 | BANKURA |  | Bankura Division | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | SM/18036 | Augmentation | Soil Investigation work for construction of OHR (200 CUM CAPACITY) under Augmentation of Indpur Piped Water Supply Scheme, Block- Bankura- I, District- Bankura. | Assistant Engineer | Junior Engineer | ORD/000886/2023-2024 | 3037/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.49 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | SM/18036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 731/BQA | 31/03/2023 |  | Resource Division | 100.35 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | SM/18036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 2732/BQA | 03/10/2023 |  | Resource Division | 4 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | SM/18036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000234/2023-2024 | 193/BQA | 22/01/2024 |  | Resource Division | 4 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | SM/18036 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Indpur piped water supply Scheme Block-Bankura-I under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000990/2023-2024 | 2850/BMD | 09/02/2024 | 07/08/2024 | M.S. ENTERPRISE | 120.1 | 0 | 0 | 30
Total | [13 empty] | 695.58 | 3.46 | 0.5