## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Hirbandh | Bankura Division | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | Sinking of 2 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) to CWR with allied works, Construction of 100 Cum. Clear Water Reservoir, Construction of Pump House, Boundary Wall, Construction of Over Head Reservoir (100 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Harirampur pipe water supply scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000485/2023-2024 | 2337/BQA | 14/08/2023 | 10/05/2024 | MANJAR ALI KHAN | 275.04 | 30.27 | 11 | 25
2 | BANKURA | Hirbandh | Bankura Division | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 0
3 | BANKURA | Hirbandh | Bankura Division | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | Preparation of Detailed Project Report for Proposed Ground Water Based Harirampur Pipe Water Supply Scheme under Bankura Division, Block : Hirbandh, District : Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001080/2023-2024 | 3543/BQA | 29/12/2023 | 28/01/2024 | LEMNISCATE | 3.03 | 0 | 0 | 90
4 | BANKURA | Hirbandh | Bankura Division | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 16.15 | 0 | 0 | 0
5 | BANKURA | Hirbandh | Bankura Division | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 8.62 | 0 | 0 | 0
6 | BANKURA | Hirbandh | Bankura Mechanical | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA |  |  | BILL/00202/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
7 | BANKURA | Hirbandh | Bankura Mechanical | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. |  |  | BILL/00303/2024-2025 | null | 10/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0 | null
8 | BANKURA | Hirbandh | Bankura Mechanical | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. |  |  | BILL/00304/2024-2025 | null | 10/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0 | null
9 | BANKURA | Hirbandh | Bankura Mechanical | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. |  |  | BILL/00305/2024-2025 | BP-2024-25-52 | 24/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0 | null
10 | BANKURA | Hirbandh | Bankura Mechanical | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | SM/18039 | New | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Harirampur piped water supply scheme Block Hirbandh under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer |  | ORD/000565/2023-2024 | 2032/BMD | 01/09/2023 | 30/12/2023 | M/S SWAPAN BANERJEE | 35.43 | 0 | 0 | 0
Total | [13 empty] | 356.83 | 30.27 | 8.48