## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Danna Piped Water Supply Scheme. | SM/18302 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DANNA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000467/2023-2024 | 2322/BQA | 14/08/2023 | 10/05/2024 | DEBAKI RANJAN SARKAR | 683.53 | 45.92 | 6.72 | 35
2 | BANKURA | Patrasayer | Bankura Division | Danna Piped Water Supply Scheme. | SM/18302 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 245.78 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Danna Piped Water Supply Scheme. | SM/18302 | New | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at TW No-I & TW No-II Premises of Nakaijuri piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000125/2024-2025 | 1073/BMSD | 05/07/2024 | 03/09/2024 | KASHINATH DEY | 4.38 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Mechanical | Danna Piped Water Supply Scheme. | SM/18302 | New | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at P/H of adjoining mouza of Danna piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrasayer, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000126/2024-2025 | 1075/BMSD | 05/07/2024 | 03/09/2024 | KINGKINI TRADERS | 4.39 | 0 | 0 | 0
5 | BANKURA | Patrasayer | Bankura Mechanical | Danna Piped Water Supply Scheme. | SM/18302 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Danna Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000171/2023-2024 | 883/BMD | 04/05/2023 | 31/10/2023 | M/S NABIN GOPAL SENGUPTA | 68.09 | 28.78 | 42.27 | 55
Total | [13 empty] | 1006.17 | 74.7 | 7.42