## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | Wayleave / Track crossing proposal with Application ID SER-ADRA-2024-WL-24 for Chak Patrasayer PWSS ( SM Code : 18401 ) |  |  | BILL/00058/2024-2025 | FHTC/04 | 26/04/2024 |  | SOUTH EASTERN RAILWAY | 0.1 | 0 | 0 | null
2 | BANKURA | Patrasayer | Bankura Division | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | Way leave / Track crossing Proposal with Application ID : SER-ADRA-2024-WL-24 for Chak Patrasayer PWSS (SM Code : 18401) ( 2nd Instalment amount ). |  |  | BILL/00179/2024-2025 | BP-78/2024-25 | 27/05/2024 |  | SOUTH EASTERN RAILWAY | 5.88 | 0 | 0 | null
3 | BANKURA | Patrasayer | Bankura Division | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR CHAK PATRASAYER PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000498/2023-2024 | 2348/BQA | 14/08/2023 | 10/05/2024 | DEBAKI RANJAN SARKAR | 772.3 | 85.91 | 11.12 | 78
4 | BANKURA | Patrasayer | Bankura Division | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 1882/BQA | 22/07/2024 |  | Resource Division | 44.32 | 0 | 0 | 0
5 | BANKURA | Patrasayer | Bankura Division | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 2011/BQA | 26/07/2024 |  | Resource Division | 19.78 | 0 | 0 | 0
6 | BANKURA | Patrasayer | Bankura Division | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 93.28 | 0 | 0 | 0
7 | BANKURA | Patrasayer | Bankura Mechanical | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | Chak Patrasaer Piped Water Supply Scheme |  |  | BILL/01615/2023-2024 | BP-2023-24-132 | 07/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0 | 0
8 | BANKURA | Patrasayer | Bankura Mechanical | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | Chak Patrasaer Piped Water Supply Scheme |  |  | BILL/01668/2023-2024 | BP-2023-24-176 | 22/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.03 | 0 | 0 | 0
9 | BANKURA | Patrasayer | Bankura Mechanical | Chak Patrasaer Piped Water Supply Scheme | SM/18401 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Chak Patrasayar Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000170/2023-2024 | 882/BMD | 04/05/2023 | 31/10/2023 | M.S. ENTERPRISE | 68.15 | 9.4 | 13.8 | 45
Total | [13 empty] | 1014.12 | 95.31 | 9.4