## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Laying HDPE pipeline with all allied works of Zone-M (Purnapani ) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2024-2025 | 1498/BQA | 18/06/2024 | 17/08/2024 | SUBHENDU BANERJEE | 8.12 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Laying HDPE pipeline from Bhurkura more to Budhkhila village to increase pressure in Budhkhila (61), Atasole (61) & Susunigeria (77) Mouza and from Rudra more to Ladda Primary School to increse pressure in Ladda(33) Mouza under Zone-J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000088/2023-2024 | 1070/BQA | 04/05/2023 | 18/06/2023 | MAYA CONSTRUCTION | 30.07 | 30.03 | 99.87 | 80
3 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Laying of pipeline and Construction & Commissioning of FHTC (Functional House Hold Tap Connection) in different mouzas of Augmentation works for Zone-P (Nachna) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000192/2024-2025 | 2135/BQA | 07/08/2024 | 06/10/2024 | TAPAN KUMAR MANDAL | 14.48 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Construction of 200 Cum. Clear Water Reservoir, Pump House, Boundary Wall, Construction of 200 Cum. Over Head Reservoir with ancillary works, Laying Rising Main, Distribution pipeline and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-L (Dhankura) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000337/2024-2025 | 2298/BQA | 03/09/2024 | 31/05/2025 | S. S. S. ENTERPRISES | 536.72 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-M (Purnapani) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000377/2023-2024 | 2070/BQA | 25/07/2023 | 07/12/2023 | AJIT KUMAR PAUL | 96.97 | 40.19 | 41.44 | 30
6 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Work Order for Laying extra HDPE pipeline in Thutasole (42) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ under Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000443/2023-2024 | 201/KSD | 18/07/2023 | 21/07/2023 | SUBHENDU BANERJEE | 0.6 | 0.29 | 48.58 | 97
7 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Work Order for Laying of UPVC pipeline at Baraban village for increasing pressure in pipeline under Augmentation works for Zone-I (Hatikheda) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/000445/2023-2024 | 253/KSD | 24/08/2023 | 08/09/2023 | S. S. S. ENTERPRISES | 0.94 | 0.94 | 99.51 | 20
8 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Work Order for Laying of UPVC pipeline at Baraban village for increasing pressure in pipeline under Augmentation works for Zone-I (Hatikheda) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/000447/2023-2024 | 255/KSD | 24/08/2023 | 08/09/2023 | S. S. S. ENTERPRISES | 0.97 | 0.97 | 100 | 20
9 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Work Order for Laying of UPVC pipeline at Indkuri village for increasing pressure in pipeline under Augmentation works for Zone-I (Hatikheda) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/000449/2023-2024 | 257/KSD | 24/08/2023 | 08/09/2023 | S. S. S. ENTERPRISES | 0.92 | 0.92 | 99.5 | 25
10 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Work Order for Laying of UPVC pipeline at Indkuri village for increasing pressure in pipeline under Augmentation works for Zone-I (Hatikheda), under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/000451/2023-2024 | 259/KSD | 24/08/2023 | 08/09/2023 | S. S. S. ENTERPRISES | 0.87 | 0.85 | 98.11 | 25
11 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kamarkuli (17) & Barda (18) mouzas of Augmentation of Zone-I (Hatikheda) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza - 2 Nos. Total Household- 315 Nos. | Assistant Engineer | Junior Engineer | ORD/000473/2022-2023 | 288/BQA | 13/02/2023 | 30/03/2023 | BEAUTY CHATTERJEE | 39.8 | 39.12 | 98.3 | 90
12 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-P (Nachna) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000476/2023-2024 | 2331/BQA | 14/08/2023 | 10/05/2024 | SUBHENDU SEKHAR GORAI | 112.19 | 67.91 | 60.53 | 30
13 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000610/2022-2023 | 567/BQA | 17/03/2023 | 29/08/2023 | M/S TARUN KUMAR PATRA | 80.09 | 49.92 | 62.34 | 40
14 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-O (Madandihi) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000709/2023-2024 | 2679/BQA | 26/09/2023 | 10/11/2023 | SRIKANTA MONDAL | 51.87 | 38.03 | 73.32 | 49
15 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000743/2023-2024 | 2740/BQA | 04/10/2023 | 30/06/2024 | AMIYA KUMAR BIT | 141.71 | 58.3 | 41.14 | 35
16 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Zone - J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000838/2023-2024 | 2964/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 4.45 | 3.69 | 82.79 | 80
17 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Zone - L (Dhankura) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000839/2023-2024 | 2965/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 2.09 | 1.04 | 50 | 90
18 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Zone - M (Purnapani) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000840/2023-2024 | 2966/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 2.97 | 2.34 | 78.94 | 94
19 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Zone - P (Nachna) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000841/2023-2024 | 2967/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 2.95 | 0.57 | 19.43 | 95
20 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Laying HDPE pipeline from Bansol More to Dhagara Post Office and interconnection with existing rising main to increase pressure in Bansol, Chaitandihi and Dhagara Mouza under Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001083/2023-2024 | 101/BQA | 08/01/2024 | 07/02/2024 | SUBHENDU BANERJEE | 16.63 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Laying HDPE pipeline to increase pressure in Dulalpur (32) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) of Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001125/2023-2024 | 246/BQA | 25/01/2024 | 24/02/2024 | BIKASH MANDAL | 6.46 | 3.14 | 48.68 | 80
23 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Laying HDPE pipeline to increase pressure in Nischintapur and Mahespur Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) of Zone-J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001127/2023-2024 | 205/BQA | 24/01/2024 | 24/03/2024 | GANGADHAR MONDAL | 20.23 | 9.4 | 46.49 | 90
24 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 02/01/2024 to 31/03/2024. | Assistant Engineer | Junior Engineer | ORD/001134/2023-2024 | 369/KSD | 29/12/2023 | 16/03/2024 | SEKH MUJTABA ALI | 0.37 | 1.16 | 312.19 | 0
25 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Laying HDPE pipeline from Bansol More to Dhagara Post Office and interconnection with existing rising main to increase pressure in Bansol, Chaitandihi and Dhagara Mouza under Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001158/2023-2024 | 377/BQA | 07/02/2024 | 31/03/2024 | SUBHENDU BANERJEE | 16.63 | 8.29 | 49.84 | 90
26 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 01/04/2024 to 30/06/2024. | Assistant Engineer | Junior Engineer | ORD/001505/2023-2024 | 136/KSD | 27/03/2024 | 13/06/2024 | SEKH MUJTABA ALI | 0.37 | 1.15 | 311.19 | 0
27 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1528/BQA | 20/06/2024 |  | Resource Division | 55.44 | 0 | 0 | 0
28 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 107.66 | 0 | 0 | 0
29 | BANKURA |  | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 2412/BQA | 18/08/2023 |  | Resource Division | 18.48 | 0 | 0 | 0
30 | BANKURA |  | Bankura Mechanical | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Proposed surface water based IBS of Dhankura for Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) Block- Ranibandh under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000149/2024-2025 | 492/BMD | 09/07/2024 | 06/11/2024 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 96.64 | 0 | 0 | 0
31 | BANKURA |  | Bankura Mechanical | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18403 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of high lift and low lift Pumping machineries with other electro-mechanical accessories at tail end & CWR site for Augmentation works for Purnapani Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000171/2024-2025 | 513/BMD | 09/07/2024 | 06/11/2024 | EASTERN INDIA SALES & SERVICE | 56.1 | 0 | 0 | 0
Total | [13 empty] | 1528.95 | 358.26 | 23.43