## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHORA DANGA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000479/2023-2024 | 2334/BQA | 14/08/2023 | 10/05/2024 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 648.29 | 44.28 | 6.83 | 30
2 | BANKURA | Patrasayer | Bankura Division | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 155.44 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for newly sunk TW No I, TW No II of Ghora danga Piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000114/2024-2025 | 425/BMD | 27/06/2024 | 25/10/2024 | RAJIB COMPANY | 50.06 | 0 | 0 | 0
Total | [13 empty] | 853.8 | 44.28 | 5.19