## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Dhulai Piped Water Supply Scheme. | SM/18753 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DHULAI PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000741/2023-2024 | 2738/BQA | 04/10/2023 | 30/06/2024 | PRINCE INDUSTRIES (INDIA) | 910.64 | 205.48 | 22.56 | 55
2 | BANKURA | Sonamukhi | Bankura Division | Dhulai Piped Water Supply Scheme. | SM/18753 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 178.78 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Dhulai Piped Water Supply Scheme. | SM/18753 | New | New Service Connection for DHULAI (JL NO-14,PLOT-1910)Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00011/2024-2025 | BP-2024-25-5 | 10/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.62 | 0 | 0 | null
4 | BANKURA | Sonamukhi | Bankura Mechanical | Dhulai Piped Water Supply Scheme. | SM/18753 | New | New Service Connection for DHULAI (JL NO-14, PLOT-2041/2108LR) Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00021/2024-2025 | BP-2024-25-6 | 10/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.39 | 0 | 0 | null
5 | BANKURA | Sonamukhi | Bankura Mechanical | Dhulai Piped Water Supply Scheme. | SM/18753 | New | New Service Connection for DHALUI (JL NO-14, PLOT-486) Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00022/2024-2025 | BP-2024-25-7 | 10/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.91 | 0 | 0 | null
6 | BANKURA | Sonamukhi | Bankura Mechanical | Dhulai Piped Water Supply Scheme. | SM/18753 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Dhulai Piped water supply scheme Block : Sonamukhi under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000531/2023-2024 | 1930/BMD | 21/08/2023 | 17/02/2024 | EASTERN INDIA SALES & SERVICE | 68.77 | 0 | 0 | 0
Total | [13 empty] | 1169.1 | 205.48 | 17.58