## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Baragaria Piped Water Supply Scheme | SM/18789 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BARAGARIA PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2023-2024 | 2743/BQA | 04/10/2023 | 30/06/2024 | GOPAL CHANDRA CHOWDHURY | 962.3 | 150.69 | 15.66 | 1
2 | BANKURA | Kotulpur | Bankura Division | Baragaria Piped Water Supply Scheme | SM/18789 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 139.21 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Mechanical | Baragaria Piped Water Supply Scheme | SM/18789 | New | New service connection at P/H-I of Barageria W/S scheme |  |  | BILL/00422/2024-2025 | BP-2024-25-99 | 21/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.36 | 0 | 0 | null
4 | BANKURA | Kotulpur | Bankura Mechanical | Baragaria Piped Water Supply Scheme | SM/18789 | New | New service connection charge at P/H-II of Bargeria W/S scheme |  |  | BILL/00530/2024-2025 | BP-2024-25-139 | 25/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.79 | 0 | 0 | null
5 | BANKURA | Kotulpur | Bankura Mechanical | Baragaria Piped Water Supply Scheme | SM/18789 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Baragaria Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 2066/BMD | 11/09/2023 | 09/03/2024 | M/S SOMA ENTERPRISES | 68.06 | 0 | 0 | 37
Total | [13 empty] | 1180.71 | 150.69 | 12.76