## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-Voltaic system for IBS Uppargora pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura | SM/15329 |  | New NET meter connection for on grid solar system at UPORGORA Intermediate Boosting Station under BMD PHE Dte. |  |  | BILL/00299/2024-2025 | BP-2024-25-63 | 24/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.63 | 0 | 0 | null
2 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-Voltaic system for IBS Uppargora pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura | SM/15329 |  | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-Voltaic system for IBS Uppargora pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 651/BMD | 17/04/2023 | 16/06/2023 | DAS ENTERPRISE | 87.36 | 41.5 | 47.51 | 95
Total | [13 empty] | 88 | 41.5 | 47.16