## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06939 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000155/2020-2021 | 1408/PD | 29/12/2020 | 12/02/2021 | SANTANU BANERJEE | 77.87 | 25.89 | 33.24 | 100
2 | PURULIA |  | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06939 | Retrofitting | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000354/2021-2022 | 104/PD | 18/01/2022 | 17/02/2022 | SANTANU BANERJEE | 18.64 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06939 | Retrofitting | Supplying & laying different dia HDPE pipe line from Barrah Siramdih to Bonkhali village under Rangamati. (Tender No.1005/EE/PD of 20210-22) |  |  | VCH/000865/2022-2023 | 121/8443142 | 23/09/2022 |  | MANATOSH SINGH | 3.52 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06939 | Retrofitting | Providing Functional house hold tap connection (FHTC) in communication with Jal Dhara/ Jal Swapna under Rangamati W/s Scheme. (Tender No. 11/SE/PMU of 2020-21) |  |  | VCH/000916/2020-2021 | 424/8443137 | 22/03/2021 |  | SANTANU BANERJEE | 51.65 | 0 | 0 | 0
Total | [13 empty] | 151.68 | 25.89 | 17.07