## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-J) | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000243/2020-2021 | 21/PSD | 13/01/2021 | 27/02/2021 | M/S ACHARJEE CONSTRUCTION | 4.5 | 0.16 | 3.57 | 100
2 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-E) (Tender No. 417/EE/PD of 2020-21) |  |  | VCH/000012/2021-2022 | BP-2021-22-41 | 19/07/2021 |  | INDRAJIT SARKAR | 2.91 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-C) (Tender No. 339/EE/PD of 2020-21) |  |  | VCH/000013/2021-2022 | BP-2021-22-42 | 19/07/2021 |  | ANUDIP SAHA | 2.62 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) |  |  | VCH/000014/2021-2022 | null | 12/04/2021 |  | M/S S & P CONSTRUCTION | 2.66 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha Block (Tender No:- 328/EE/PD of 2020-21) |  |  | VCH/000121/2021-2022 | BP-2021-22-52 | 20/07/2021 |  | BHAGABANDAS KUMAR | 10.04 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Satra village of Hensia G.P. under command area of Satra W/S Scheme at Arsha Block (Part- H) (Tender No:- 21/EE/PD of 2021-22) |  |  | VCH/000122/2021-2022 | BP-2021-22-53 | 20/07/2021 |  | PRATIK SAHA | 2.8 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-F) (Tender No.317/EE/PD of 2020-21) |  |  | VCH/000181/2021-2022 | BP-2021-22-81 | 23/08/2021 |  | RAKSHIT ENTERPRISE | 2.57 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-I) (Tender No.350/EE/PD of 2020-21) |  |  | VCH/000182/2021-2022 | BP-2021-22-97 | 23/08/2021 |  | S.K IRFAN | 2.94 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-A) (Tender No.287/EE/PD of 2020-21) |  |  | VCH/000183/2021-2022 | BP-2021-22-83 | 16/08/2021 |  | GYANRANJAN SEN | 3.01 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Harnama & Nimdiha village of Beldih G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.304/EE/PD of 2020-21) |  |  | VCH/000184/2021-2022 | BP-2021-22-91 | 23/08/2021 |  | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 9.31 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Patuara, Hinduhir & Dharmerbera (Bhamarbera) village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No:- 263/EE/PD of 2020-21) |  |  | VCH/000219/2021-2022 | null | 09/08/2021 |  | SUBODH PRAMANIK | 31.87 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) |  |  | VCH/000241/2021-2022 | BP-2021-22-44 | 19/07/2021 |  | M/S. S.P CONSTRUCTION | 2.66 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Prviding Functional HouseholdTapConnection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-G) (Tender No. 284/EE/PD of 2020-21) |  |  | VCH/000327/2021-2022 | BP-2021-22-122 | 11/10/2021 |  | TUSHAR KANTI GORAI | 3.69 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Prviding Functional HouseholdTapConnection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-B) (Tender No. 338/EE/PD of 2020-21) |  |  | VCH/000328/2021-2022 | BP-2021-22-117 | 11/10/2021 |  | SIDDHARTHA SANKAR SARKAR | 3.85 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-K) (Tender No.352/EE/PD of 2020-21) |  |  | VCH/000329/2021-2022 | BP-2021-22-119 | 11/10/2021 |  | SIDDHARTHA SANKAR SARKAR | 3.16 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-J) (Tender No.269/EE/PD of 2020-21) |  |  | VCH/000330/2021-2022 | BP-2021-22-135 | 11/10/2021 |  | M/S ACHARJEE CONSTRUCTION | 3.43 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1 & 2 ) alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Kansai River) at Satra under Satra W/S Scheme under Purulia Sadar Sub Division of Purulia Division, PHE Dte. (Tender No.863/EE/PD of 2021-22) |  |  | VCH/000807/2021-2022 | BP-2021-22-235 | 03/02/2022 |  | SUBODH PRAMANIK | 9.7 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-C) (Tender No.339/EE/PD of 2020-21) |  |  | VCH/000985/2021-2022 | BP-2021-22-245 | 16/02/2022 |  | ANUDIP SAHA | 0.92 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-E) (Tender No.417/EE/PD of 2020-21) |  |  | VCH/000986/2021-2022 | BP-2021-22-242 | 16/02/2022 |  | INDRAJIT SARKAR | 1.05 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Laying op UPVC pipe as distribution main (Loop Line) from Satra Junior High School to Satra uppar para for drinking water supply through FHTC meet up the water crisis at Satra W/s Scheme. (Tender No.864/EE/PD of 2021-2022) |  |  | VCH/000988/2021-2022 | BP-2021-22-239 | 16/02/2022 |  | SUBODH PRAMANIK | 7.31 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Harnama and Nimdih village of Beldih G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.304/EE/PD of 2020-21) |  |  | VCH/001004/2021-2022 | BP-2021-22-262 | 28/02/2022 |  | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 0.23 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-D) (Tender No.264/EE/PD of 2020-21) |  |  | VCH/001006/2021-2022 | BP-2021-22-254 | 25/02/2022 |  | M/S. S.P CONSTRUCTION | 0.96 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-H) (Tender No.21/EE/PD of 2021-22) |  |  | VCH/001007/2021-2022 | BP-2021-22-256 | 25/02/2022 |  | PRATIK SAHA | 1.66 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.328/EE/PD of 2020-21) |  |  | VCH/001008/2021-2022 | BP-2021-22-255 | 28/02/2022 |  | BHAGABANDAS KUMAR | 4.89 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Patuara, Hinduhir & Dharmerbera (Bhamarbera) village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.263/EE/PD of 2020-21) |  |  | VCH/001011/2021-2022 | BP-2021-22-259 | 28/02/2022 |  | SUBODH PRAMANIK | 7.97 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-I). (Tender No.350/EE/PD of 2020-21) |  |  | VCH/001018/2021-2022 | BP-2021-22-260 | 28/02/2022 |  | S.K IRFAN | 0.64 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07567 | Retrofitting | Laying of UPVC pipe as distribution main (loop line) from Misirdih More near Canel to Jhunjka village including PWD Road Crossing (Tamna-Arsha Road) by Jack pushing for drinking water supply through FHTC to meet up the water crisis at Jhunjka Village of Satra W/s Scheme under JJM. (Tender No.871/EE/PD of 2021-22) |  |  | VCH/001139/2021-2022 | BP-2021-22-293 | 09/03/2022 |  | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 18.23 | 0 | 0 | 0
Total | [13 empty] | 145.57 | 0.16 | 0.11