## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07841 | Retrofitting | Supplying , fitting and fixing Cast Iron heavy type spiral stair case at Parbeliya under Parbeliya W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000580/2022-2023 | 492/RNP | 02/08/2022 | 12/08/2022 | SUBHAS CHANDRA MAHATO | 1.58 | 0 | 0 | 95
2 | PURULIA |  | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07841 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza-Gosaindih, Parbeliya, Gopaldhawh, Parbeliya City under Bhamuria & Saltore G.P) (493 nos.) (Tender No.324/EE/PD of 2020-21) |  |  | VCH/000811/2021-2022 | BP-2021-22-227 | 03/02/2022 |  | TAPAN CHANDRA | 22.48 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07841 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B ( Mouza- Parbeliya City , Parbelia under Bhamuria & Saltore G.P). (1364Nos.) (Tender No. 402/EE/PD of 2021-22) |  |  | VCH/000887/2021-2022 | BP-2021-22-243 | 16/02/2022 |  | ASHOK KUMAR CHATTERJEE | 49.23 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07841 | Retrofitting | Supplying fitting and fixing cast iron heavy type spiral stair case at Parbeliya under Parbeliya W/S Scheme of Raghunathpur Sub- Division, PHE Dte. (Tender No- 544/2022-23 of EE/PD) |  |  | VCH/001050/2022-2023 | BP-2022-23-394 | 20/10/2022 |  | SUBHAS CHANDRA MAHATO | 1.43 | 0 | 0 | 0
Total | [13 empty] | 74.71 | 0 | 0