## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Construction of 5.0 x 3.0 mtr size Meter Room including approach road, plinth protection, surface drain etc. complete for Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000038/2023-2024 | 656/PD | 17/05/2023 | 25/08/2023 | SUDHANSHU OJHA | 4.92 | 3.23 | 65.67 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Construction of 5.0 x 3.0 mtr size Switch Room cum Chlorine Room approach road, plinth protection, surface drain etc. complete for Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000222/2021-2022 | 741/PSD | 13/12/2021 | 11/02/2022 | KABERI DUTTA | 4.57 | 4 | 87.5 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Repairing, renovation and changing of filter media of filter bed including cleaning the tube settler to enhancement the filteration rate of water to meet up water crisis at Hutmura WTP of Hutmura W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000235/2021-2022 | 745/PSD | 13/12/2021 | 02/01/2022 | SHYAMAL KUMAR DEY | 2.22 | 1.65 | 74.19 | 85
4 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Repairing and renovation of the Over Head reservoir (OHR) of 30000 gallon Capacity, Staging Height 20 mtr. at Hutmura WTP campus under Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000266/2021-2022 | 1544/PD | 15/12/2021 | 13/02/2022 | M/S KARUNAMOYEE CONSTRUCTION | 7.26 | 4.52 | 62.3 | 85
5 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Hutmura W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000268/2021-2022 | 1545/PD | 15/12/2021 | 13/02/2022 | SHYAMAL KUMAR DEY | 10.73 | 0.96 | 8.96 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Laying of 200 mm dia DI (K9) pipe as rising main from intake site to WTP under Hutmura Water Supply Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000304/2021-2022 | 1594/PD | 17/12/2021 | 16/01/2022 | SHYAMAL KUMAR DEY | 5.7 | 0.93 | 16.34 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000346/2021-2022 | 96/PD | 18/01/2022 | 04/03/2022 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 26.3 | 0.07 | 0.25 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Hutmura mouza (Jl. No.139) & Phulberia mouza (Jl. No.140) under Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000347/2021-2022 | 97/PD | 18/01/2022 | 19/03/2022 | M/S KARUNAMOYEE CONSTRUCTION | 72.9 | 10.75 | 14.75 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Sidpur mouza (Jl. No.154) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000348/2021-2022 | 98/PD | 18/01/2022 | 29/03/2022 | M/S KARUNAMOYEE CONSTRUCTION | 82.79 | 24.38 | 29.45 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Extention / replacement of distribution pipe line in different habitation of Hutmura mouza (Jl. No.139) & Phulberia mouza (Jl. No.140) for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000425/2021-2022 | 358/PD | 04/03/2022 | 18/04/2022 | PREMNATH MITRA | 121.12 | 23.08 | 19.05 | 63
11 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Karcha mouza (Jl. No.151) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000460/2021-2022 | 422/PD | 17/03/2022 | 01/05/2022 | SHYAMAL KUMAR DEY | 31.94 | 5.05 | 15.81 | 75
12 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Additional Pipe laying of 50 mm dia (OD) for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000500/2022-2023 | 440/PSD | 24/06/2022 | 09/07/2022 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 2.48 | 2.21 | 89.17 | 90
13 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Extension of pipe line in distribution system for Stand Post at different School & ICDS Centre of Purulia-II Block to supply drinking water of command area including road crossing of pipe line and replacement of Sluice Valve on delivery pipe line at OHR Campus and distribution main at field of Hutmura Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000606/2022-2023 | 504/PSD | 12/08/2022 | 21/09/2022 | M/S KARUNAMOYEE CONSTRUCTION | 4.14 | 4.11 | 99.3 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Karcha mouza (Jl. No.151) of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000782/2022-2023 | 1629/PD | 03/11/2022 | 18/12/2022 | SHYAMAL KUMAR DEY | 9.56 | 5.61 | 58.69 | 60
15 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 1628/PD | 31/12/2021 |  | Resource Division | 26.12 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 389/PD | 11/03/2022 |  | Resource Division | 0.72 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Repairing, renovation & restoration of pump house & Chlorine cum Alum dozing room at Hutmura WTP campus of Hutmura W/s Scheme. (Tender No.831/EE/PD of 2021-22) |  |  | VCH/000176/2022-2023 | BP-2022-23-41 | 02/05/2022 |  | TARASANKAR DEY | 2.44 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Extension/ replacement of distribution pipe line in different habitation of Hutmura Mouza (Jl No. 139) & Phulberia mouza (JL No 140) for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under augmentation of Hutmura Water Supply Scheme of Purulia II Block under Purulia Sadar Sub- Division under Purulia Division, PHE Dte. (Tender No- 27/2021-22 of SE/PMU/WBPWSP) |  |  | VCH/000889/2022-2023 | BP-2022-23-76 | 01/07/2022 |  | PREMNATH MITRA | 53.19 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Laying of 200 mm dia DI k9 pipe as rising main from intake site to WTP under Hutmura W/S Scheme of Purulia Sadar Sub- Division, under Purulia Division, PHE Dte (Tender No- 868/2021-22 of EE/PD) |  |  | VCH/000893/2022-2023 | BP-2022-23-73 | 01/07/2022 |  | SHYAMAL KUMAR DEY | 1.04 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum with other allied works at Hutmura W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No. 867/EE/PD of 2021-22) |  |  | VCH/000904/2022-2023 | BP-2022-23-97 | 07/07/2022 |  | SHYAMAL KUMAR DEY | 8.46 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation of Korcha mouza (JL No- 151) and replacement/extension of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 13/2022-23 of EE/PD) |  |  | VCH/000955/2022-2023 | BP-2022-23-136 | 19/07/2022 |  | SHYAMAL KUMAR DEY | 17.28 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.920/EE/PD of 2021-22) |  |  | VCH/001013/2022-2023 | BP-2022-23-277 | 22/09/2022 |  | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 12.26 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing FHTC in connection with JJM and JAL SWAPNA at different habitation of Hutmura Mouza JL No 139 & Phulberia Mouza JL No 140 under Hutmura Water Supply Scheme of Purulia II Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 05/2022-23 of EE/PD) |  |  | VCH/001019/2022-2023 | BP-2022-23-308 | 26/09/2022 |  | M/S KARUNAMOYEE CONSTRUCTION | 37.94 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Supply and delivery of 6mm N.B. gun Metal Ferrule for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation of Hutmura Mouza (JL No 139) & Phulberia mouza (JL No 140) under Hutmura Water Supply Scheme of Purulia II Block under Purulia Division, PHE Dte. (Tender No- 445/2022-23 of EE/PD) |  |  | VCH/001020/2022-2023 | BP-2022-23-310 | 26/09/2022 |  | M/S KARUNAMOYEE CONSTRUCTION | 4.76 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Repairing renovation & restoration of Store cum Guard room at Hutmura WTP campus of Hutmura W/s Scheme. (Tender No.893/EE/PD of 2021-22) |  |  | VCH/001124/2021-2022 | BP-2021-22-392 | 30/03/2022 |  | TAPAN CHANDRA | 1.82 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.920/EE/PD of 2021-22) |  |  | VCH/001128/2021-2022 | BP-2021-22-368 | 29/03/2022 |  | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 10.34 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Hutmura W/S Scheme Block- Purulia-II) to be Augmentation/ Rejuvenation (Tender No- 540/2021-22 of EE/PD) |  |  | VCH/001169/2021-2022 | BP-2021-22-303 | 21/03/2022 |  | INDRANIL DUTTA & ASSOCIATES | 3.97 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Hutmura W/S Scheme Block- Purulia-II) to be Augmentation/ Rejuvenation (Tender No- 849/2021-22 of EE/PD) |  |  | VCH/001176/2021-2022 | BP-2021-22-302 | 21/03/2022 |  | INDRANIL DUTTA & ASSOCIATES | 1.07 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Repairing renovation & restoration of switch cum meter room including roof treatment at Hutmura Dam site of Hutmura W/S Scheme under Purulia Sadar Sub- Division (Tender No- 837/2021-22 of EE/PD) |  |  | VCH/001188/2021-2022 | BP-2021-22-319 | 22/03/2022 |  | INDRAJIT SARKAR | 2.27 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Sidpur mouza (Jl. No.154) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 1007/2021-22 of EE/PD) |  |  | VCH/001216/2021-2022 | BP-2021-22-347 | 28/03/2022 |  | M/S KARUNAMOYEE CONSTRUCTION | 27.68 | 0 | 0 | 0
31 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | New connection for Hutmura high lift Water supply scheme |  |  | BILL/00822/2023-2024 | BP-23-24-282 | 16/02/2024 |  | WBSEDCL PURULIA | 7.07 | 0 | 0 | 0
32 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Hutmura(OHR site) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000024/2023-2024 | 395/PMD | 06/04/2023 | 05/06/2023 | MOON LIGHT HOUSE | 7.36 | 2.26 | 30.76 | 100
33 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Internal and external illumination with other allied works for augmentation of Hutmura W/S scheme(both intake & OHR site) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000056/2023-2024 | 525/PMD | 05/05/2023 | 04/07/2023 | ASISH KR. SEN | 5.12 | 4 | 78.2 | 100
34 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Hutmura Water Supply scheme Block Purulia-II under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000065/2022-2023 | 397/PMD | 16/06/2022 | 16/07/2022 | SUBRATA DUTTA | 20.51 | 20.45 | 99.71 | 100
35 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Repairing, overhauling thorough repairing of floating walkway with required MS work by necessary supply of materials and other allied works at Hutmura (Low Lift) w/s scheme under PMD PHE Dte. in the district of Purulia. |  |  | ORD/000168/2021-2022 | 78/PMSD (W/S) | 08/03/2022 | 15/03/2022 | SUBRATA DUTTA | 4.6 | 3.7 | 80.43 | 80
36 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Augmentation of floating walkway lowering and anchoring of existing repaired floating barge with required ms work by necessary supply of materials and other allied works at Hutmura(Low Lift) W/S scheme under PMD PHE Dte in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000342/2022-2023 | 124/PMD | 15/02/2023 | 16/04/2023 | ASHOKE ADHIKARY | 7.85 | 7.01 | 89.31 | 0
37 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Supply, Delivery and installation of submersible pumping machineries with flexible hose pipe, MCC panel, flowmeter with other allied works for augmentation of Hutmura(Intake side) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000422/2022-2023 | 240/PMD | 03/03/2023 | 02/05/2023 | KHITISH CH. PATHAK | 18.86 | 4.01 | 21.29 | 30
38 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, MCC panel, flowmeter and other allied works at Hutmura(OHR site) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000423/2022-2023 | 241/PMD | 03/03/2023 | 02/05/2023 | SUBRATA DUTTA | 50.17 | 41.82 | 83.36 | 100
39 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Supply, fixing of PVC pipe,cable,valve etc and other allied works at Hutmura (low lift) Site water supply scheme under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000502/2024-2025 | 1305/PMD | 03/09/2024 | 23/09/2024 | KHITISH CH. PATHAK | 3.39 | 0 | 0 | 0
40 | PURULIA |  | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | Augmentation | Enhancement of contract demand load for Augmentation of Hutmura Water Supply Scheme |  |  | VCH/000429/2022-2023 | null | 03/11/2022 |  | WBSEDCL PURULIA | 3.08 | 0 | 0 | 0
Total | [13 empty] | 726 | 173.81 | 23.94