## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on i) Balrampur-Barabazar-Sindri Road from 16.780 Km to 18.90 Km and Barabazar-Bandwan Road from 0.00 Km to 0.76 Km in respect of Augmentation of Barabazar water supply scheme in the District of Purulia. |  |  | BILL/00174/2022-2023 | BP-2022-23-663 | 23/02/2023 |  | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 48.28 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. |  |  | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 |  | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Construction of WBSEDCL Meter Room & Guard Room with sanitary and plumbing arrangment at Barabazar River Site for Augmentation of Barabazar W/S Scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte.. | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000057/2023-2024 | 663/PD | 17/05/2023 | 25/08/2023 | CHATTERJEE CONSTRUCTION | 7.69 | 4.57 | 59.4 | 60
4 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Repairing ,renovation & Construction Damaged (Portion) of Boundary Wall of Brabazar OHR Side Campus Of Barabazar W/S Scheme Under Purulia Division ,PHE DTE.. | Assistant Engineer |  | ORD/000278/2021-2022 | 1553/PD | 15/12/2021 | 29/01/2022 | DEBASISH CHAKRABORTY | 10.02 | 4.89 | 48.87 | 55
5 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I) | Assistant Engineer | Junior Engineer | ORD/000421/2021-2022 | 312/PD | 25/02/2022 | 11/04/2022 | KOUSHIK CHATTERJEE | 152.12 | 81.03 | 53.27 | 84
6 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capcaity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Rejuvanation of Barabazar W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000431/2021-2022 | 378/PD | 11/03/2022 | 06/12/2022 | PRAVAT SARKAR | 70.29 | 64.62 | 91.94 | 93
7 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II) | Assistant Engineer | Junior Engineer | ORD/000432/2021-2022 | 379/PD | 11/03/2022 | 10/05/2022 | PRAVAT SARKAR | 91.16 | 0 | 0 | 80
8 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Guarding arrangement through Registered firm organized by Ex-Military person at Barabazar OHR site of Barabazar W/S Scheme under Purulia Division, PHE Dte. (w.e.f. 01.04.2022 to 30.04.2022) | Assistant Engineer |  | ORD/000504/2021-2022 | 530/4/PD | 30/03/2022 | 29/04/2022 | FRONTLINE EX-SERVICEMEN BUREAU | 0.58 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-III,Habitation-Ankro,GP- Ankro- Barakadam of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-II) (Habitation-Ankro,GP- Ankro- Barakadam ) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000608/2022-2023 | 517/PSD | 12/08/2022 | 21/09/2022 | SADHAN GORAIN | 3.51 | 2.31 | 65.71 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Making Interconnection and Bypass arrangemet of Rising Main and Distribution Pipeline For Newly Constructed OHR at Barabazar OHR Site of Aug. Barabazar W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001209/2022-2023 | 493/PD | 31/03/2023 | 15/05/2023 | KOUSHIK CHATTERJEE | 8.09 | 0 | 0 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Sinking of 02 Nos 200 mm dia rig bored tubewell by DTH method of drilling (200 mm X 165 mm) at augmentation of Barabazar Water Supply Scheme (River Site) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001323/2023-2024 | 1709/PD | 04/12/2023 | 18/01/2024 | CHATTERJEE CONSTRUCTION | 9.26 | 5.09 | 54.95 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Sinking of 02 Nos 200 mm dia rig bored tubewell by DTH method of drilling (200 mm X 165 mm) at augmentation of Barabazar Water Supply Scheme (River Site) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001491/2023-2024 | 1802/PD | 08/12/2023 | 07/01/2024 | KOUSHIK CHATTERJEE | 9.26 | 5.28 | 57.05 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Repairing of Guard Room at Barabazar OHR Site under Barabazar W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001493/2023-2024 | 1804/PD | 08/12/2023 | 07/01/2024 | CHATTERJEE CONSTRUCTION | 1.88 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Repairing of Boundary wall & DI Rising Main at Barabazar River Site under Barabazar W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. |  |  | ORD/001871/2023-2024 | 96/PD | 15/01/2024 | 15/03/2024 | CHATTERJEE CONSTRUCTION | 14.67 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 1509/PD | 13/12/2021 |  | Resource Division | 6.46 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 242/PD | 20/02/2023 |  | Resource Division | 6.4 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub- Division, PHE Dte. Part-II (Tender No- 1012/2021-22 of EE/PD) |  |  | VCH/000914/2022-2023 | BP-2022-23-122 | 16/07/2022 |  | PRAVAT SARKAR | 27.6 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of capacity 100 cum with other allied works at Barabazar W/s Scheme. (Tender No.1013/EE/PD of 2021-22) |  |  | VCH/001166/2021-2022 | BP-2021-22-345 | 28/03/2022 |  | KOUSHIK CHATTERJEE | 7.9 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/s Scheme, Block Purulia-I, Barabazar) to be Augmentation / Rejuvenation under Purulia Division P.H.E. Dte. (SL No.07) (Tender No.357/EE/PD of 2021-22) |  |  | VCH/001214/2021-2022 | BP-2021-22-369 | 30/03/2022 |  | INDRANIL DUTTA & ASSOCIATES | 3.55 | 0 | 0 | 0
20 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | New Connection for Augmentation of Barabazar W/S Scheme. |  |  | BILL/00244/2023-2024 | BP-23-24-154 | 14/09/2023 |  | WBSEDCL PURULIA | 3.74 | 0 | 0 | 0
21 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Barabazar and other Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000010/2021-2022 | 19/PMD | 19/01/2022 | 18/02/2022 | RABINDRA NATH KHAN | 13.59 | 2.57 | 18.88 | 79
22 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Barabazar water supply scheme under PMD, PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000052/2023-2024 | 521/PMD | 05/05/2023 | 04/07/2023 | GOENKA ENTERPRISE | 36.99 | 18.82 | 50.88 | 60
23 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Barabazar Water Supply scheme Block Barabazar under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000063/2021-2022 | 108/PMD | 28/02/2022 | 30/03/2022 | M/S M S ENTERPRISE | 20.48 | 5.88 | 28.73 | 100
24 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Supply, Delivery and Installation & Commissioning of Chlorination Arrangement at Barabazar OHR for Augmentation of Barabazar water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 1090/PMD | 08/07/2024 | 06/09/2024 | MOUSUMI BENERJEE | 10.14 | 4.61 | 45.47 | 0
25 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Supply delivery and installation of Submersible pumping machinery with all ancillaries & auxiliaries works for Augmentation of Barabazar Water Supply Scheme under PMD PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000189/2022-2023 | 766/PMD | 14/11/2022 | 21/11/2022 | MOUSUMI BENERJEE | 3.24 | 2.91 | 89.75 | 90
26 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Supply, delivery and Installation of Submersible pumping machineries for newly constructed tube wells and other allied works for Augmentation of Barabazar W/S scheme under PMD Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000264/2024-2025 | 1233/PMD | 13/08/2024 | 02/09/2024 | MOUSUMI BENERJEE | 6.56 | 0 | 0 | 0
27 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Internal and external illumination with other allied works for augmentation of Barabazar water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000405/2022-2023 | 233/PMD | 03/03/2023 | 02/05/2023 | AVISHEK ENTERPRISE | 4.86 | 2.25 | 46.27 | 30
28 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed tube well with allied cable line and other allied works for augmentation of Barabazar w/s scheme under PMD, PHE Dte. in the District of Purulia. |  | JUNIOR ENGINEER | ORD/000406/2022-2023 | 234/PMD | 03/03/2023 | 02/05/2023 | MOUSUMI BENERJEE | 9.65 | 4.31 | 44.67 | 20
29 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Supply delivery and installation of 75 KVA voltage stabilizer for Augmentation of Barabazar water supply scheme under PMD PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000407/2022-2023 | 235/PMD | 03/03/2023 | 02/05/2023 | MOUSUMI BENERJEE | 7.6 | 6.7 | 88.24 | 35
30 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | External illumination of OHR site barabazar water supply scheme for Augmentation work under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000439/2023-2024 | 419/PMD | 11/03/2024 | 10/05/2024 | BISHWANATH NANDI | 7.55 | 4.06 | 53.86 | 30
31 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | Supply and laying of 1.1 KV grade 3.5 core 95 sq. mm XLPE insulated Al. armoured cable for Augmentation at Barabazar W/S Scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000537/2023-2024 | 499/PMSD(W/S) | 21/12/2023 | 05/01/2024 | MOUSUMI BENERJEE | 0.62 | 0.25 | 40 | 100
32 | PURULIA |  | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | Augmentation | CONSTRUCTION OF RIG BORE TUBE WELL (200 x165) MM DIA BY DTH METHOD FOR BARABAZAR AND OTHER SCHEMES UNDER PMD PHE DTE.(TR.NO 60 OF 2022-23) |  |  | VCH/000230/2022-2023 | C072218251845 | 18/07/2022 |  | RABINDRA NATH KHAN | 8.16 | 0 | 0 | 0
Total | [13 empty] | 614.22 | 220.15 | 35.84