## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00087/2022-2023 | BP-2022-23-5174 | 02/01/2023 |  | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 7.37 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Daily Operation and Maintenance of rising main and distribution system, sluice valve, street stand post etc. under Chitmu W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. (w.e.f. 01.09.2017 to 31.08.2018) | Assistant Engineer |  | ORD/000001/2017-2018 | 1269/PD | 31/08/2017 | 31/08/2018 | BHAGABANDAS KUMAR | 3.52 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Chitmu W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000273/2021-2022 | 1549/PD | 15/12/2021 | 15/03/2022 | BHAGABANDAS KUMAR | 10.72 | 0 | 0 | 85
4 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft ) of capacity 100 cum and staging height 20 mtr. with including supply of all labour & materials for Chitmu W/S Scheme under Purulia Sadar Sub-Division, Purulia Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000275/2021-2022 | 1550/PD | 15/12/2021 | 11/09/2022 | KOUSHIK CHATTERJEE | 43.13 | 37.59 | 87.16 | 100
5 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room from Chitmu Pump House to distribution area through distribution main of Chitmu W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000276/2021-2022 | 1551/PD | 15/12/2021 | 15/03/2022 | BHAGABANDAS KUMAR | 16.63 | 0 | 0 | 100
6 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sl no. 1) | Assistant Engineer |  | ORD/000405/2021-2022 | 284/PD | 17/02/2022 | 03/04/2022 | MS D.PALIT AND CO. | 140.81 | 34.77 | 24.69 | 65
7 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Additional work for laying 63 mm dia(OD) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Chitmu mouza under Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000503/2022-2023 | 439/PSD | 24/06/2022 | 09/07/2022 | MS D.PALIT AND CO. | 3.31 | 3.04 | 91.62 | 95
8 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Continuation work for Soil Investigation work for proposed 100 M3 capacity Over Head Reservoir of Chitmu W/S Scheme under Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/001002/2022-2023 | 111/PD | 20/01/2023 | 19/02/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 1.53 | 54.93 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Repairing of damaged pipe line & Stand post at different location and construction of new stand post at primary school & ICDS center of Chitmu village to supply drinking water under Chitmu Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/001050/2022-2023 | 282/PD | 27/02/2023 | 19/03/2023 | BHAGABANDAS KUMAR | 1.23 | 1.23 | 99.99 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Construction of Boundary wall with other allied works at OHR site of Chitmu W/S Scheme under Purulia Sadar Sub-Division of Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001130/2022-2023 | 410/PD | 21/03/2023 | 05/05/2023 | SAZID HOSSEN ANSARI | 16.07 | 7.97 | 49.58 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 1505/PD | 13/12/2021 |  | Resource Division | 10.96 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 388/PD | 11/03/2022 |  | Resource Division | 7.56 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-I Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No-22/2021-22 of SE/PMU/WBPWSP(P) ) |  |  | VCH/000944/2022-2023 | BP-2022-23-100 | 16/07/2022 |  | MS D.PALIT AND CO. | 22.49 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Chitmu W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. (Tender No.873/EE/PD of 2021-22) |  |  | VCH/001011/2022-2023 | BP-2022-23-272 | 21/09/2022 |  | BHAGABANDAS KUMAR | 7.79 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sl no. 1) |  |  | VCH/001130/2021-2022 | BP-2021-22-366 | 29/03/2022 |  | MS D.PALIT AND CO. | 19.51 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chitmu W/S Scheme Blalarampur W/s Scheme (Zone-I) Block Jhalda-II & Balarampur) to be Augmented / Rejuvenation under Purulia Division P.H.E. Dte. (Tender No.358/EE/PD of 2021-22) |  |  | VCH/001212/2021-2022 | BP-2021-22-372 | 29/03/2022 |  | ROY CHOWDHURY ASSOCIATES | 1.39 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Full deposit scheme for Chitmu water pump under Jhalda CCC |  |  | BILL/00253/2023-2024 | BP-2023-24-147 | 15/09/2023 |  | WBSEDCL PURULIA | 2.45 | 0 | 0 | 0
18 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Chitmu W/S Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000016/2021-2022 | 20/PMD | 19/01/2022 | 05/03/2022 | M/S D. PALIT & CO. | 30.6 | 0 | 0 | 0
19 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply delivery and installation of Flowmeter & 50KVA voltage stabilizer and with others allied works at Chitmu water supply scheme under , PMD, PHE;Dte.in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000016/2023-2024 | 387/PMD | 06/04/2023 | 05/06/2023 | M/S UJJAL DIESEL SERVICE | 7.49 | 7.49 | 100 | 100
20 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply delivery and installation of pumping machineries with Allied works at Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000022/2022-2023 | 306/PMD | 06/05/2022 | 05/06/2022 | RABINDRA NATH KHAN | 35.6 | 29.77 | 83.63 | 85
21 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries,, with all ancillaries & auxiliaries including allied works at CWR side pump house at Chitmu Water Supply Scheme,under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000023/2023-2024 | 394/PMD | 06/04/2023 | 05/06/2023 | M S ENTERPRISE | 33.26 | 18.54 | 55.75 | 100
22 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Chitmu Water Supply scheme Block Jhalda-II under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000083/2021-2022 | 168/PMD | 07/03/2022 | 06/04/2022 | CINZANO | 20.5 | 13.97 | 68.17 | 70
23 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply, delivery and installation of lighting arrangement at pump house with other allied works for Augmentation of Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000179/2023-2024 | 1150/PMD | 17/10/2023 | 16/11/2023 | M/S UJJAL DIESEL SERVICE | 4.75 | 1.69 | 35.7 | 100
24 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply delivery and installation of 2 MT capacity HOT Crane with other allied works for Augmentation of Chitmu Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000204/2023-2024 | 1194/PMD | 03/11/2023 | 02/01/2024 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 8.27 | 4.14 | 50 | 100
25 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply delivery and laying of cable line and installation of kiosk at Chitmu water supply scheme under PMD, PHE, Dte. in purulia district. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000243/2024-2025 | 1231/PMD | 13/08/2024 | 12/09/2024 | M/S UJJAL DIESEL SERVICE | 2.99 | 0 | 0 | 0
26 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply, delivery and fitting-fixing of ST pole and laying of cable line for Illumination arrangement at pumphouse site with other allied works under Chitmu w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000551/2023-2024 | 377/PMD | 04/03/2024 | 03/05/2024 | M/S UJJAL DIESEL SERVICE | 5.56 | 0.16 | 2.82 | 65
27 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Supply, delivery and fitting-fixing of MS pipe, valves and dismantling joint at Chitmu W/S scheme under P.M.D. P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000559/2023-2024 | 72/PMSD(W/S) | 23/02/2024 | 09/03/2024 | M S ENTERPRISE | 0.94 | 0.46 | 49.62 | 100
28 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 616/PMD | 01/06/2023 |  | Resource Division | 0.34 | 0 | 0 | 0
29 | PURULIA |  | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | Augmentation | LOAD ENHANCEMENT APPLICATION FOR CHITMU WATER SUPPLY SCHEME UNDER PMD PHE DTE. |  |  | VCH/000325/2022-2023 | BP-2022-23-39 | 08/09/2022 |  | WBSEDCL PURULIA | 1.7 | 0 | 0 | 0
Total | [13 empty] | 469.73 | 162.35 | 34.56