## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on Begunkodar-Arsha Road in respect of Augumentation of Jhalda (Rural Part) water supply scheme JJM in the District of Purulia. |  |  | BILL/00063/2022-2023 | BP-2022-23-511 | 22/12/2022 | 22/12/2022 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 12.93 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Making Xerox copy of original DPR, Drawing, Mouza Map etc. |  |  | BILL/00248/2023-2024 | 27/2023-149 | 30/05/2023 | 30/05/2023 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under Jhalda-II Block under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/000002/2023-2024 | 525/PD | 10/04/2023 | 25/04/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 3.21 | 0 | 0 | 100
4 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Laying of distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation under Zone-1A command area of Jhalda W/S Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Phase-II, Zone-1A, Part-I, GP-Begunkodar, Habitation-Murguma, Narayanpur Alias Lakhipur) | Assistant Engineer | Junior Engineer | ORD/000008/2023-2024 | 536/PD | 12/04/2023 | 27/05/2023 | BOSE CONSTRUCTION | 14.61 | 0 | 0 | 100
5 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Augementation of Jhalda Water Supply Scheme (Rural Part) (Zone-II, Part-IV) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Habitation-Supurdih and Brindabanpur, Gp-Begunkodar) | Assistant Engineer |  | ORD/000072/2022-2023 | 649/PD | 22/04/2022 | 06/06/2022 | BHAGABANDAS KUMAR | 21.02 | 0 | 0 | 100
6 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Repairing , renovation & Construction Damaged (portion) of Boundary Wall of Masina Pump House Campus Of Jhalda W/S Scheme Under Purulia Division ,PHE DTE... | Assistant Engineer | Junior Engineer-1 | ORD/000163/2023-2024 | 934/PD | 19/07/2023 | 18/08/2023 | CHATTERJEE CONSTRUCTION | 9.37 | 0 | 0 | 80
7 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) | Assistant Engineer |  | ORD/000301/2022-2023 | 827/PD | 17/05/2022 | 01/07/2022 | M/S S & P CONSTRUCTION | 153.83 | 0 | 0 | 85
8 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-II) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II-Chatambari Habitation, GP- Begunkodar) | Assistant Engineer |  | ORD/000345/2021-2022 | 68/PD | 17/01/2022 | 03/03/2022 | BHAGABANDAS KUMAR | 35.23 | 0 | 0 | 85
9 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under Zone-1A command area of Augementation of Jhalda Water Supply Scheme (Rural Part) of Jhada II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Zone-1A, Part-I, GP-Begunkodar, Habitation-Murguma, Narayanpur Alias Lakhipur) | Assistant Engineer | Junior Engineer-3 | ORD/000401/2021-2022 | 253/PD | 10/02/2022 | 11/04/2022 | BOSE CONSTRUCTION | 73.43 | 0 | 0 | 100
10 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Laying of DI distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) in Mouza-Jaharhatu, Habitation-Gurrabera under command area (Zone-IB) of Augementation of Jhalda Water Supply Scheme (Rural Part) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000402/2021-2022 | 254/PD | 10/02/2022 | 12/03/2022 | KANAILAL PAL | 10.08 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Repairing, renovation & restoration of Store room including at Masina Pump House site of Jhalda W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000442/2021-2022 | 92/PSD | 14/03/2022 | 13/04/2022 | CHATTERJEE CONSTRUCTION | 3.58 | 0 | 0 | 95
12 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-III) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-III-Jaharhatu,Nischantapur Habitation, GP- Bamnia-Beladh) | Assistant Engineer |  | ORD/000444/2021-2022 | 408/PD | 15/03/2022 | 14/05/2022 | ZAKIR HOSSIN MONDAL | 90.73 | 0 | 0 | 98
13 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Emergent Dismantling of R.C.C. Elevator Reservoir, Capacity 681 Cum (Intze Type), Staging height 20 meter at Jhalda Municipality OHR site including By pass arrangement for direct supply due to Dismantling of Jhalda OHR with allied works of Jhalda W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000508/2021-2022 | 632(1-2)/PD | 24/11/2021 | 23/01/2022 | ANUP KUMAR SAHA | 24.06 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Withdrawing & relaying of AC pipe line from Birsamor to Sramik Kalyan Kendra, Namopara to Kumarkuli Road and installation of sluice valve and Repairing of valve chamber at Jhalda under Jhalda Municipality W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000615/2022-2023 | 512/PSD | 12/08/2022 | 11/09/2022 | SK MANIR | 2 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in Goverment Office,Health Centre, ICDS Centre,SSK,MSK, Primary School ,High school at Jhalda Municipalty Under Jhalda Municipalty Water Supply Scheme of Jhalda-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I) | Assistant Engineer | Junior Engineer-1 | ORD/000619/2022-2023 | 516/PSD | 12/08/2022 | 01/07/2023 | SEKH IRFAN | 0.92 | 0 | 0 | 100
16 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Laying of parallel distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) | Assistant Engineer |  | ORD/000868/2022-2023 | 1810/PD | 06/12/2022 | 06/09/2023 | M/S S & P CONSTRUCTION | 28.57 | 0 | 0 | 80
17 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supplying delivery fitting& fixing of 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-1 Block in Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001230/2022-2023 | 252/PSD | 31/03/2023 | 05/04/2023 | R.K ENTERPRISE | 0.65 | 0 | 0 | 100
18 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supplying delivery fitting& fixing of 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-1 Block in Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001232/2022-2023 | 253/PSD | 31/03/2023 | 05/04/2023 | R.K ENTERPRISE | 0.43 | 0 | 0 | 100
19 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supplying delivery fitting& fixing of 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-2 Block in Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001234/2022-2023 | 255/PD | 31/03/2023 | 05/04/2023 | R.K ENTERPRISE | 0.63 | 0 | 0 | 70
20 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supplying delivery fitting& fixing of 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-2 Block in Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001235/2022-2023 | 254/PSD | 31/03/2023 | 05/04/2023 | R.K ENTERPRISE | 0.42 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 1564/PD | 16/12/2021 | 16/12/2021 | Resource Division | 70.09 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 393/PD | 11/03/2022 | 11/03/2022 | Resource Division | 3.18 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 240/PD | 20/02/2023 | 20/02/2023 | Resource Division | 83.68 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-II) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II-Chatambari Habitation, GP- Begunkodar) (Tender No.947/EE/PD of 2021-22) |  |  | VCH/000143/2022-2023 | BP-2022-23-26 | 07/04/2022 | 07/04/2022 | BHAGABANDAS KUMAR | 18.69 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Jhalda Municipality W/S Scheme block-Jhalda-I) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 360/2021-22 of EE/PD) |  |  | VCH/000940/2022-2023 | BP-2022-23-105 | 16/07/2022 | 16/07/2022 | ROY CHOWDHURY ASSOCIATES | 0.97 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, part- I) of Jhalda-II Block under Purulia Sadar Sub- Division, PHE Dte. (Part-I Begunkodar Habitation G.P. Begunkodar) (Tender No- 34/2022-23 of SE/PMU/WBPWSP(P) ) |  |  | VCH/000948/2022-2023 | BP-2022-23-112 | 16/07/2022 | 16/07/2022 | M/S S & P CONSTRUCTION | 49.46 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-III) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-III-Jaharhatu,Nischantapur Habitation, GP- Bamnia-Beladh) (Tender No- 149/2022-23 of EE/PD) |  |  | VCH/001059/2022-2023 | BP-2022-23-405 | 20/10/2022 | 20/10/2022 | ZAKIR HOSSIN MONDAL | 67.77 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) (Tender No.34/SE/PMU of 2022-23) |  |  | VCH/001060/2022-2023 | BP-2022-23-408 | 20/10/2022 | 20/10/2022 | M/S S & P CONSTRUCTION | 35.71 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Preparation of DPR (consultancy work) in connection with Functional household Connection of different existing PWSS Jhalda Aug. W/S Scheme (Rural Part) Block- Jhalda-II) to be Augmentation/ Rejuvenation (Tender No- 540/2021-22 of EE/PD) |  |  | VCH/001165/2021-2022 | BP-2021-22-322 | 22/03/2022 | 22/03/2022 | M/S TECH VISION | 4.69 | 0 | 0 | 0
30 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | New Connection for Augmentation at Begunkodar O.H.R near H.S School, Po begunkadar Ps Kotshila. |  |  | BILL/00849/2023-2024 | BILL/00849/2023 | 01/03/2024 | 01/03/2024 | WBSEDCL PURULIA | 0.41 | 0 | 0 | 0
31 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Jhalda Water Supply scheme Block Jhalda under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2021-2022 | 113/PMD | 28/02/2022 | 30/03/2022 | ANUP KUMAR SAHA | 20.47 | 0 | 0 | 100
32 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Replacement of essential item on the intake Burge of Jhalda Augmentation W/S Scheme under P.M.D., P.H.E.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000183/2023-2024 | 1173/PMD | 03/11/2023 | 01/01/2025 | ANUP KUMAR SAHA | 6.21 | 0 | 0 | 50
33 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Providing external illumination arrangement at WTP area of Jhalda Aug WTP under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000230/2023-2024 | 1206/PMD | 03/11/2023 | 02/01/2024 | ANUP KUMAR SAHA | 2.74 | 0 | 0 | 100
34 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, MCC panel and with necessary substitutes and allied works at the intake of the Jhalda Augmentation w/s project under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000254/2022-2023 | 44/PMD | 19/01/2023 | 02/01/2025 | ANUP KR. SAHA | 43.88 | 0 | 0 | 70
35 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supply, delivery and installation of centrifugal pumping machineries, MCC panel, Flowmeter With necessary substitutes and allied works at WTP area of Jhalda Augmentation w/s project under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000270/2022-2023 | 45/PMD | 19/01/2023 | 20/03/2023 | SUNRISE ENGINEERING CORPORATION | 49.44 | 0 | 0 | 60
36 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at OHR site for Augmentation of Jhalda Water Supply scheme Block Jhalda under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000291/2022-2023 | 83/PMD | 01/02/2023 | 02/12/2024 | ANUP KR. SAHA | 21.57 | 0 | 0 | 100
37 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supply of flexible hose pipe on the intake Burge of Jhalda Augmentation water supply scheme under PMD, PHE, Dte. |  |  | ORD/001037/2024-2025 | 88/PMSD(W/S) | 24/02/2025 | 26/03/2025 | ANUP KUMAR SAHA | 0.71 | 0 | 0 | 0
38 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Supply, delivery & installation of Lighting conductor, Glow sign board & illumination at intake barge under Jhalda Aug water supply scheme under Purulia Mechanical Division, P.H.E Dte. in District Purulia. |  |  | ORD/001039/2024-2025 | 73/PMSD(W/S) | 12/02/2025 | 14/03/2025 | MUKHERJEE CONSTRUCTION | 0.57 | 0 | 0 | 0
39 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 618/PMD | 01/06/2023 | 01/06/2023 | Resource Division | 1.55 | 0 | 0 | 0
40 | PURULIA |  | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | Augmentation | SUPPLY DELIVERY & INSTT OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF JHALDA W/S SCHEME UNDER PMD PHE DTE.(TR.NO 343 OF 2021-22) |  |  | VCH/000084/2022-2023 | C042211566405 | 08/04/2022 | 08/04/2022 | ANUP KR. SAHA | 12.25 | 0 | 0 | 0
Total | [13 empty] | 980.14 | 0 | 0