## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. |  |  | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 |  | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Repairing of DI rising main pipeline including cleaning of chokage & Construction of 100 Cum capacity RCC clear water reservoir (CWR) and Construction of Meter Room, Panel Room, undercut pump house with other allied works at river site campus and providing 456 nos functional household tap connection at chirka mouza in connection with Jal Jeevan Mission (JJM) for Augmentation of Sindri-ChasmoreW/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000037/2023-2024 | 655/PD | 17/05/2023 | 16/07/2023 | SB CONSTRUCTION | 59.68 | 20.99 | 35.18 | 100
3 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM) and Jal Sapna at Chirka village of Garaphushara G.P. under command area of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-B) | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000061/2022-2023 | 171/PSD | 18/04/2022 | 13/05/2022 | SK ABBAS | 4.85 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supplying & laying of HDPE pipe line for Distribution System of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-A) | Assistant Engineer | Junior Engineer-1 | ORD/000079/2022-2023 | 629/PD | 22/04/2022 | 06/06/2022 | ZEST INFRACON | 68.48 | 2.23 | 3.26 | 100
5 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Laying of Left out Loop Pipe Line for distribution System at Sindri and Garafusro Mouza under command area of Sindri Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte . |  |  | ORD/000216/2024-2025 | 1085/PD | 07/06/2024 | 06/08/2024 | SADHAN GORAIN | 24.37 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supplying & laying of HDPE pipe line for Distribution System of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Garaphushara & Sindri Mouza) | Assistant Engineer | Junior Engineer-1 | ORD/000343/2022-2023 | 852/PD | 23/05/2022 | 07/07/2022 | SADHAN GORAIN | 296.78 | 184.3 | 62.1 | 90
7 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Laying of MS pipe distribution line at Garafusro under command area of Sindri Chasmore W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000447/2024-2025 | 1509/PD | 27/08/2024 | 11/10/2024 | SADHAN GORAIN | 32.27 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Repairing and renovation of the Over Head reservoir (OHR) of 250 m3 Capacity, Staging Height 20 mtr. of Sindri-Chasmore W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000737/2022-2023 | 1477/PD | 20/09/2022 | 19/12/2022 | SADHAN GORAIN | 11.8 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Construction of RCC common manifold camber and Laying of 250 mm dia DI rising main from manifold chamber to CWR at river site of Sindri- chas more W/S scheme in connection of Jal Jeevan Mission (JJM) under Sindri-chas more W/S scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000879/2023-2024 | 1529/PD | 16/10/2023 | 30/11/2023 | SADHAN GORAIN | 11.86 | 5.91 | 49.87 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Pushing of 600mm dia MS pipe and 100 mm dia MS water carrier pipe by hydraulic jacking method across Purulia to Jhalda Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission at 04 (Four) different location Near Chas more for Sindri Chasmore W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001620/2023-2024 | 1830/PD | 12/12/2023 | 10/02/2024 | MS GORAIN CONCERN | 41.39 | 0 | 0 | 45
11 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Repairing of DI rising main pipeline including cleaning of chokage & Construction of Boundary wall, pathway and landfilling with other allied works at river site of Sindri Chasmore W/S Scheme of Purulia Sadar Sub-Divn. under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001621/2023-2024 | 1831/PD | 12/12/2023 | 10/02/2024 | M/S SB CONSTRUCTION | 18.02 | 9 | 49.94 | 70
12 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Repairing & renovation of 100 cum capacity CWR & Pump house, Boundary Wall (OHR Site and River Site) & Tranformar room, Meter room with Guard room at Sindri-Chasmore river site Pump house campus of Sindri-Chsmore W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001814/2023-2024 | 42/PD | 09/01/2024 | 09/03/2024 | M/S SB CONSTRUCTION | 21.36 | 0 | 0 | 90
13 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Laying of 250 mm dia MS Pipe and Road Crossing and Construction of PCC Approach Road at OHR site for Sindri-Chas W/S Scheme in connection with FHTC connection under Jal Jeevan Mission (JJM) Programme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/003966/2023-2024 | 509/PD | 16/03/2024 | 15/05/2024 | SADHAN GORAIN | 22.84 | 0 | 0 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supplying & laying of HDPE pipe line for Distribution System of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-A) (Tender No- 315/2022-23 of EE/PD) |  |  | VCH/001035/2022-2023 | BP-2022-23-383 | 19/10/2022 |  | ZEST INFRACON | 45.52 | 0 | 0 | 0
15 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Enhancement of the contract demand from 80 KVA at 0.4 KV to 105/105//105//105//105 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE SINDRI CHASMORE Water Supply, (Consumer ID -942413800) |  |  | BILL/00865/2023-2024 | BP-23-24-308 | 19/03/2024 |  | WBSEDCL PURULIA | 1.44 | 0 | 0 | 0
16 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supply and installation of 2 M.T capacity single girder H.O.T crane with gantry girder and square rail for Sindrichasmore w/s scheme new CWR Pump house under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000049/2024-2025 | 968/PMD | 20/06/2024 | 19/08/2024 | RABINDRA NATH KHAN | 8.09 | 4.04 | 50 | 100
17 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Internal and external illumination with other allied works for augmentation of existing pump house & new CWR pump house of Sindrichasmore water supply scheme under Purulia Mechanical Division , PHE Dte .in the District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000054/2024-2025 | 972/PMD | 20/06/2024 | 19/08/2024 | COMBINE ENTERPRISES | 18.83 | 0 | 0 | 0
18 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supply of valves, pipes and miscellaneous works for new proposed CWR & existing P.H of Sindrichasmore w/s scheme under PMD, PHE Dte. in the district Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 995/PMD | 21/06/2024 | 20/08/2024 | RABINDRA NATH KHAN | 1.61 | 0 | 0 | 0
19 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Providing internal and external illumination arrangement at proposed CWR of Sindrichasmore W/S under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000153/2023-2024 | 649/PMD | 08/06/2023 | 07/08/2023 | MAHIPAL MAJHI | 6.13 | 0.91 | 14.78 | 5
20 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, flowmeter with necessary substitutes and allied electrical panel at existing pump house at Augmentation of Sindri chasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000365/2022-2023 | 207/PMD | 28/02/2023 | 29/04/2023 | RABINDRA NATH KHAN | 66.49 | 34.42 | 51.77 | 60
21 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supply and lowering of submersible pump motor sets at at newly constructed River Bed Tubewell with supply of necessary substitutes at Augmentation of Sindri chasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000366/2022-2023 | 208/PMD | 28/02/2023 | 29/04/2023 | RABINDRA NATH KHAN | 17.88 | 10.75 | 60.11 | 85
22 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, Voltage Stabilizer with necessary substitutes and allied electrical panel at for Proposed CWR at intake side of Sindrichasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000376/2022-2023 | 206/PMD | 28/02/2023 | 29/04/2023 | RABINDRA NATH KHAN | 31.34 | 17.08 | 54.51 | 15
23 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Sindrichasmore Water Supply scheme Block Purulia-II under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000382/2022-2023 | 213/PMD | 28/02/2023 | 30/03/2023 | TAPAN KUMAR DEY | 21.61 | 12.88 | 59.59 | 60
24 | PURULIA |  | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | Augmentation | Rectification of different feeders of Beldi W/S scheme(Low lift) for Augmentation of Beldi W/S Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000441/2023-2024 | 421/PMD | 11/03/2024 | 10/04/2024 | TAPAN KUMAR DEY | 5.21 | 0 | 0 | 30
Total | [13 empty] | 840.17 | 302.52 | 36.01