## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Making Xerox copy of original DPR, Drawing, Mouza Map etc. |  |  | BILL/00248/2023-2024 | 27/2023-149 | 30/05/2023 |  | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Construction of Toilet, Repairing of Guard Room & Remaining work of Pump House (Phase-II) at Sarbari under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000139/2024-2025 | 910/PD | 07/05/2024 | 06/07/2024 | AMIT PATHAK | 7.1 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Crossing of PWD Road and laying of additional HDPE pipe line(75mm & 63mm) with allied work (Zone-I) under Sarbari W/S Scheme within Raghunathpur Sub-Division under Purulia Division,PHEDte. | Assistant Engineer | Junior Engineer-1 | ORD/000212/2024-2025 | 1080/PD | 07/06/2024 | 22/07/2024 | JAYANTA KUMAR MONDAL | 33.85 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Laying of DI(k-9) pipe and other allied works for rising main under Sarbari W/S Scheem within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2022-2023 | 844/PD | 23/05/2022 | 07/07/2022 | KHITISH CHANDRA PATHAK | 30.86 | 16.93 | 54.85 | 80
5 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | New Sinking of 2 (Two) nos. 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. [Part-A] | Assistant Engineer |  | ORD/000320/2022-2023 | 853/PD | 23/05/2022 | 22/06/2022 | KHITISH CHANDRA PATHAK | 7.79 | 6.77 | 86.95 | 90
6 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | New Sinking of 2 (Two) nos. 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. [Part-B] | Assistant Engineer |  | ORD/000321/2022-2023 | 854/PD | 23/05/2022 | 22/06/2022 | KHITISH CHANDRA PATHAK | 7.79 | 2.13 | 27.41 | 95
7 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Construction of Pump House (10 X 7 mtr) at Head Work site under Sarbari W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000332/2022-2023 | 863/PD | 23/05/2022 | 31/08/2022 | M/S SHYAMASHREE ENTERPRISE | 15.57 | 6.77 | 43.51 | 100
8 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-II) of Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Mouza-Neturia, Pathardiha, Kuthibari, Nawada) | Assistant Engineer | Junior Engineer | ORD/000365/2022-2023 | 868/PD | 23/05/2022 | 22/07/2022 | KHITISH CHANDRA PATHAK | 72.9 | 63.1 | 86.56 | 75
9 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Sarbari W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/000402/2022-2023 | 341/RNP | 01/06/2022 | 01/07/2022 | K.S.GROUP | 1.4 | 1.4 | 100 | 100
10 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supplying, laying different dia HDPE and DI pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-I) of Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000411/2022-2023 | 984/PD | 22/06/2022 | 06/08/2022 | JAYANTA KUMAR MONDAL | 356.05 | 279.86 | 78.6 | 85
11 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Withdrawing and new laying of necessary M.S. carrier pipe and all allied works at Ramkanali Ranipur village Railway Track at Erekusum village and new sinking of 2(two) no. 200 mm dia. River bed vertical at River Damodar with supplying and laying 100 mm dia GI collecting line from Riverbed Tubewell to CWR through common manifold chamber at river bank and execution of additional works for construction of (10.0 mtr x 7.0) mtr pump house drain, plinth protection under Saltora-Hijuli Under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. |  |  | ORD/000466/2024-2025 | 1523/PD | 27/08/2024 | 11/09/2024 | M/S SAYAK BHATTACHARYA | 43.79 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Tubewell (for 3 & 4) under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000661/2023-2024 | 1354/PD | 13/09/2023 | 13/10/2023 | KHITISH CHANDRA PATHAK | 5.56 | 2.77 | 49.93 | 100
13 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 400 cum and staging height 20 mtr. with including supply of all labour & materials for Sarbari W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000922/2022-2023 | 1889/PD | 15/12/2022 | 11/09/2023 | MD AAMIR KHAN | 131.92 | 72.32 | 54.82 | 100
14 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Construction of Pump House (9 mtr X 4 mtr) at Boosting Station (Phase-II) under Sarbari W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000968/2022-2023 | 47/PD | 09/01/2023 | 19/04/2023 | AMIT PATHAK | 10.66 | 10.44 | 97.94 | 100
15 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Repairing and renovation of low-lift Pump House at River Side including drain under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001086/2022-2023 | 97/RNP | 13/03/2023 | 28/03/2023 | AMIT PATHAK | 0.97 | 0.96 | 99.31 | 0
16 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Road Crossing of rising main by jack pushing at Panchyet Road under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003964/2023-2024 | 507/PD | 16/03/2024 | 15/05/2024 | KHITISH CHANDRA PATHAK | 9.36 | 8.85 | 94.59 | 100
17 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Laying of HDPE pipe line (75mm & 63mm) with additional Functional Household Tap Connection (FHTC) of distribution system (Zone-I) under Sarbari W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/003977/2023-2024 | 522/PD | 16/03/2024 | 15/05/2024 | JAYANTA KUMAR MONDAL | 32.71 | 25.57 | 78.16 | 0
18 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Laying of HDPE pipe line (75mm & 63mm) and supplying of DI specials with additional Functional Household Tap Connection (FHTC) of distribution system (Zone-I) under Sarbari W/S scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/003978/2023-2024 | 523/PD | 16/03/2024 | 15/05/2024 | JAYANTA KUMAR MONDAL | 30.53 | 11.93 | 39.07 | 0
19 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply fitting fixing D.I Specials for 200 MM dia D.I Rising Main under Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/003979/2023-2024 | 524/PD | 16/03/2024 | 30/04/2024 | KHITISH CHANDRA PATHAK | 4.75 | 1.66 | 34.99 | 100
20 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Laying of different dia HDPE Pipe line and Road crossing for additional work at Sarbori distribution line (Zone-II) under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003980/2023-2024 | 525/PD | 16/03/2024 | 15/05/2024 | KHITISH CHANDRA PATHAK | 15.1 | 9.47 | 62.74 | 100
21 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Boosting Station under Sarbari W/S Scheme (Phase-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/003982/2023-2024 | 528/PD | 16/03/2024 | 14/06/2024 | AMIT PATHAK | 18.35 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 978/PD | 22/06/2022 |  | Resource Division | 239.56 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | New sinking of 02 (Two) No. 200 mm dia river bed vertical tube well T/W no- 3&4 along with necessary 100 mm dia GI collecting line in connection with FHTC from river bed tube well to common manifold chamber at river bank (Damodar river) at Chinakuri Ghat under Sarbari Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 744/2021-22 of EE/PD) |  |  | VCH/000958/2022-2023 | BP-2022-23-131 | 19/07/2022 |  | ASHOK KUMAR CHATTERJEE | 5.05 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Sarbari W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 972/2021-22 of EE/PD) |  |  | VCH/000967/2022-2023 | BP-2022-23-141 | 19/07/2022 |  | HORIZEN | 2.35 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Sarbari W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 542/2021-22 of EE/PD) |  |  | VCH/000968/2022-2023 | BP-2022-23-134 | 19/07/2022 |  | HORIZEN | 4.09 | 0 | 0 | 0
26 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | QUATATION FOR SHIFTING OF TRANSFORMER |  |  | BILL/00476/2023-2024 | BP-23-24-238 | 13/12/2023 |  | WBSEDCL PURULIA | 2.36 | 0 | 0 | 0
27 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works for Augmentation at SARBARI (Phase-1) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2023-2024 | 644/PMD | 08/06/2023 | 08/07/2023 | AVISHEK ENTERPRISE | 6.27 | 6.27 | 99.91 | 100
28 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works for Rejuvenation at SARBARI (Phase-2) w/s scheme under PMD, PHE Dte. in the District of Purulia.. |  | JUNIOR ENGINEER | ORD/000117/2023-2024 | 645/PMD | 08/06/2023 | 08/07/2023 | SANTU MITRA | 4.4 | 3.99 | 90.68 | 50
29 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply, Delivery and installation of Centrifugal pumping machineries, MCC Panels with others allied works for rejuvenation at SARBARI PHASE-2 w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000185/2023-2024 | 1175/PMD | 03/11/2023 | 02/03/2024 | R.N.S. TRADING | 41.91 | 0 | 0 | 0
30 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply and installation of 2 MT Capacity single girder H.O.T Crane with gantry girder and square rail for Sarbori Phase-1 Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000201/2023-2024 | 1191/PMD | 03/11/2023 | 02/01/2024 | SEN BROTHERS | 9.71 | 9.28 | 95.57 | 100
31 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply and installation of 2 MT Capacity single girder H.O.T Crane with gantry girder and square rail for Sarbori Phase-2 Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000202/2023-2024 | 1192/PMD | 03/11/2023 | 02/01/2024 | P K ENGINEERING | 11.49 | 0 | 0 | 0
32 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sarbari Water Supply scheme Neturia Block under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000292/2022-2023 | 84/PMD | 01/02/2023 | 02/04/2023 | GHOSE ENGINEERING SYNDICATE | 21.61 | 16.33 | 75.56 | 100
33 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries, MCC Panel, Flowmeter with others allied works for Augmentation at SARBARI PHASE-1 w/s scheme under PMD, PHE, Dte. in the District of Purulia |  | JUNIOR ENGINEER | ORD/000309/2022-2023 | 97/PMD | 03/02/2023 | 04/04/2023 | GOENKA ENTERPRISE | 49.77 | 40.16 | 80.69 | 100
34 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Supply, delivery and installation of 4 nos. submersible pumps motor sets at newly constructed riverbed tubewell with other allied works for Augmentation at SARBARI PHASE-1 w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000310/2022-2023 | 98/PMD | 03/02/2023 | 04/04/2023 | AVISHEK ENTERPRISE | 12.13 | 9.86 | 81.3 | 0
35 | PURULIA |  | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 617/PMD | 01/06/2023 |  | Resource Division | 3.1 | 0 | 0 | 0
Total | [13 empty] | 1251.17 | 606.83 | 48.5