## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under Raghunathpur-II Block under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2023-2024 | 527/PD | 10/04/2023 | 25/04/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.95 | 4.94 | 99.94 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Construction of Guard Room at WTP Campus under Raghunathpur Pipe Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2023-2024 | 664/PD | 17/05/2023 | 25/08/2023 | BISWAJIT MAJI | 6.34 | 5.22 | 82.33 | 100
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Ketlapur Mouza, JL No.-82, Plot No.-2790 under Para Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 767/PD | 08/06/2023 | 07/08/2023 | PARTHA SARATHI SAHABABU | 10.96 | 4.35 | 39.68 | 100
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 500 Cum with other allied works at Boosting Station under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001043/2022-2023 | 275/PD | 27/02/2023 | 28/05/2023 | BOSE CONSTRUCTION | 56.66 | 22.78 | 40.2 | 70
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Laying of distribution pipe line ( 90 mm,75mm & 63 mm dia HDPE pipe ) towards Garhpanchkot Prakriti Kendra under Raghunathpur W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001140/2022-2023 | 418/PD | 21/03/2023 | 05/05/2023 | CHANDAN CHATTERJEE | 10.97 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-I A/I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001197/2022-2023 | 471/PD | 28/03/2023 | 27/05/2023 | ASHOK KUMAR CHATTERJEE | 261.64 | 101.35 | 38.74 | 35
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), Construction of 250 Cum OHR and other allied works of Raghunathpur Water Supply Scheme (Zone-I A/II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001198/2022-2023 | 472/PD | 28/03/2023 | 23/12/2023 | ASHOK KUMAR CHATTERJEE | 360.46 | 102.63 | 28.47 | 30
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Continuation work order for the work of Daily Maintenance for Beautification of existing gardens and all vacant places within the residential compound at Lakshmanpur WTP of Raghunathpur water supply Project within Raghunathpur Sub-Division under Purulia Division, P.H.E.Dte. ( w.e.f. 01.04.2023 to 31.03.2024) | Assistant Engineer | Junior Engineer | ORD/001326/2022-2023 | 0137/RNP | 30/03/2023 | 30/03/2024 | ASHOKE KUMAR CHATTERJEE | 4.86 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply & delivery of spreading and levelling Filter media at Rapid Gravity sand filter beds after removal of existing not functioning filter media at Laxmanpur WTP under Purulia Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/003455/2023-2024 | 317/PD | 01/03/2024 | 30/04/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 15.86 | 12.03 | 75.88 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Sinking of 1(One) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Boosting Pump Station (Seleta Mouza) of Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003989/2023-2024 | 518/PD | 16/03/2024 | 30/04/2024 | SUBRATA SINGHADEO | 3.87 | 2.37 | 61.26 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 75/PD | 17/01/2023 |  | Resource Division | 14.94 | 0 | 0 | 0
12 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | For new connection at Gobag near uposasthya kendra under augmentation of Raghunathpur zone 1A/1 & zone 1A/II |  |  | BILL/00777/2023-2024 | BP-23-24-277 | 01/02/2024 |  | WBSEDCL PURULIA | 2.81 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone 1A/II under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000124/2023-2024 | 860/PMD | 20/07/2023 | 19/08/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 7.42 | 34.37 | 75
Total | [13 empty] | 775.92 | 263.09 | 33.91