## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | SM/15336 | Augmentation | Repairing, renovation of Boundary Wall at WTP & OHR site of Hutmura W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000165/2023-2024 | 936/PD | 19/07/2023 | 18/08/2023 | M/S. DESTINY CONSTRUCTION | 9.67 | 3.85 | 39.79 | 100
2 | PURULIA |  | Purulia Division | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | SM/15336 | Augmentation | Repairing of Baffle Floculator ,Tube Settlor and Construction of Platform of Preasure Filter and Construction of Boundary wall and Repairing of Old Staff Room and other allied works under Hutmura & Bandwan W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . |  |  | ORD/000338/2024-2025 | 1364/PD | 25/07/2024 | 23/09/2024 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 91.07 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | SM/15336 | Augmentation | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 650 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Hutumura W/S Scheme for source augmentation | Assistant Engineer | Junior Engineer-1 | ORD/000542/2023-2024 | 1339/PD | 08/09/2023 | 06/03/2024 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 248.15 | 37.22 | 15 | 40
4 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | SM/15336 | Augmentation | Supply, delivery and installation of Open well Submersuble pumping machinery for direct pumping with others electro-mechanical work at Hutmura W/S (OHR Site) under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000064/2024-2025 | 993/PMD | 21/06/2024 | 20/08/2024 | SUBRATA DUTTA | 15.59 | 0 | 0 | 0
5 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | SM/15336 | Augmentation | Priming arrangement for two nos centrifugal pump and two back wash pump and other allied works at Hutmura (OHR) Site water supply scheme under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000065/2024-2025 | 994/PMD | 21/06/2024 | 20/08/2024 | SUBRATA DUTTA | 1.06 | 0.53 | 49.71 | 100
Total | [13 empty] | 365.54 | 41.6 | 11.38