## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) (for Kasmali Mouza (part) | AE/Ulu |  | ORD/000152/2020-2021 | 1607/HD | 09/11/2020 | 09/12/2020 | CONSTRUCTION CORNER | 28.68 | 5.44 | 18.96 | 100
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (for Kasmali Mouza(part) | AE/SADAR |  | ORD/000153/2020-2021 | 1608/HD | 09/11/2020 | 09/12/2020 | CONSTRUCTION CORNER | 28.67 | 1.76 | 6.15 | 100
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) (for Kasmali Mouza(part) | AE/Ulu |  | ORD/000154/2020-2021 | 1617/HD | 09/11/2020 | 09/12/2020 | S RAHA ENTERPRISE | 16.6 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) & School, AWC from existing distribution system at Kharigeria mouza of Kasmali W/S scheme under Amta-II Block under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000271/2022-2023 | 353/AE/USD | 22/08/2022 | 06/10/2022 | BANERJEE ENTERPRISE | 1.85 | 1.74 | 94.43 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-3). | AE/Ulu |  | ORD/000351/2022-2023 | 435/AE/USD | 13/09/2022 | 28/10/2022 | MA MANASA CONSTRUCTION | 4.78 | 4.47 | 93.4 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-6). | AE/Ulu | JE/USD | ORD/000354/2022-2023 | 438/AE/USD | 13/09/2022 | 28/10/2022 | MA MANASA CONSTRUCTION | 4.81 | 4.83 | 100.37 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-7). | AE/Ulu | JE/USD | ORD/000355/2022-2023 | 439/AE/USD | 13/09/2022 | 28/10/2022 | MA MANASA CONSTRUCTION | 4.77 | 4.75 | 99.57 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Construction of balance portion of boundary wall at 2nd TW site of Kasmali W/S scheme in Uluberia Sub-division, under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000389/2022-2023 | 477/AE/USD | 16/09/2022 | 31/10/2022 | M/S HOWRAH CONSTRUCTION | 3.34 | 3.29 | 98.58 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection (FHTC) from existing distribution system of Kasmali pipe water supply scheme under Amta-II Block under Howrah Division, PHE Dte. |  |  | VCH/000847/2021-2022 | 844320 | 24/03/2022 | 24/03/2022 | S RAHA ENTERPRISE | 1.51 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme |  |  | VCH/000883/2020-2021 | 844363 | 25/03/2021 | 25/03/2021 | BANERJEE ENTERPRISE | 8.99 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme |  |  | VCH/000895/2020-2021 | 844386 | 26/03/2021 | 26/03/2021 | S RAHA ENTERPRISE | 15.64 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | SM/06714 | Retrofitting | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme |  |  | VCH/001009/2020-2021 | 844375 | 25/03/2021 | 25/03/2021 | STEELCONC AND ASSOCIATES | 2.17 | 0 | 0 | 0
Total | [13 empty] | 121.82 | 26.28 | 21.57