## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-J) | AE/SADAR |  | ORD/000130/2020-2021 | 1542/HD | 05/11/2020 | 05/12/2020 | A P POWER & CONCRETE | 18.83 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-K) | AE/SADAR |  | ORD/000131/2020-2021 | 1543/HD | 05/11/2020 | 05/12/2020 | GHOSH CONCERN | 18.88 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-L) | AE/SADAR |  | ORD/000132/2020-2021 | 1544/HD | 05/11/2020 | 05/12/2020 | GHOSH CONCERN | 18.86 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Gobindapur piped water supply scheme under Jagatballavpur Blockunder Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Part-M) | AE/SADAR |  | ORD/000226/2020-2021 | 1406/HD | 16/10/2020 | 15/11/2020 | MONIRUL ISLAM | 4.79 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | AE/SADAR |  | ORD/000421/2021-2022 | 335/HD | 17/02/2022 | 19/03/2022 | MS ARPAN ENTERPRISE | 2.97 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Work Order for Laying of 90 mm dia 490 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-V) (Part-B) | AE/SADAR |  | ORD/000430/2021-2022 | 344/HD | 17/02/2022 | 19/03/2022 | A.P. POWER & CONCRETE | 2.13 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-V)Part C | AE/SADAR |  | ORD/000431/2021-2022 | 345/HD | 17/02/2022 | 19/03/2022 | M/S ASHIRBAD (INDIA) | 4.01 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Work Order for Laying of 75 mm dia at node piont 41-27 and 20-15 node point for. 110mm dia,Total 1265 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-IV) | AE/SADAR |  | ORD/000516/2021-2022 | 504/HD | 08/03/2022 | 28/03/2022 | A.P. POWER & CONCRETE | 4.92 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000208/2021-2022 | W/183 | 18/08/2021 |  | A.P. POWER & CONCRETE | 16.29 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000210/2021-2022 | W/218 | 18/08/2021 |  | ALOK ENTERPRISE | 11.75 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000211/2021-2022 | W/217 | 18/08/2021 |  | ALOK ENTERPRISE | 16.11 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Laying of 90mm dia 490 mtr lenght additional UPVC pipe line for retrofitting work for FHTC of Gobindapur PWSS. |  |  | VCH/000784/2022-2023 | 84439 | 22/09/2022 |  | A P POWER & CONCRETE | 2.12 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Consumption of Laying of 75 mm dia at node point 41-15 and 20-15 node point for 110 mm dia total 1265 mtr length additional UPVC pipe line for FHTC within the command area of Gobindapur PWSS (Phase-IV) |  |  | VCH/000790/2022-2023 | 84438 | 22/09/2022 |  | A P POWER & CONCRETE | 4.91 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. |  |  | VCH/000815/2022-2023 | 844310 | 22/09/2022 |  | MONIRUL ISLAM | 4.62 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Relaying of pipe line of 110 mm dia 75 mm at node point for Retrofitting Gobindapur W/S Scheme under HSSD. |  |  | VCH/000821/2022-2023 | 844313 | 26/09/2022 |  | BUILT INDIA | 3.42 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting Gobindapur W/S Scheme. |  |  | VCH/000876/2021-2022 | 844334 | 30/03/2022 |  | ALOK ENTERPRISE | 15.52 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | SM/06782 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000881/2021-2022 | 844333 | 30/03/2022 |  | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 13.74 | 0 | 0 | 0
Total | [13 empty] | 163.87 | 0 | 0