## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Work Order for Additional Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte.(Part-G) (Phase-I) | AE/Ulu | JE/USD | ORD/000097/2022-2023 | 111/AE/USD | 15/06/2022 | 30/07/2022 | MAITY CONSTRUCTIONS | 4.89 | 0.6 | 12.26 | 100
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Kasra Mouza (Part) | AE/Ulu | JE/USD | ORD/000108/2020-2021 | 1503/HD | 04/11/2020 | 04/12/2020 | PRADIP KUMAR JATI | 28.98 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kasra Mouza (Part) | AE/Ulu | JE/USD | ORD/000109/2020-2021 | 1504/HD | 04/11/2020 | 04/12/2020 | DEV DAS SHOW | 18.74 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Bara Mahara Mouza) | AE/Ulu | JE/USD | ORD/000120/2020-2021 | 1515/HD | 04/11/2020 | 04/12/2020 | PRADIP KUMAR JATI | 30.15 | 3.19 | 10.57 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-3) | AE/Ulu | JE/USD | ORD/000300/2021-2022 | 2231/HD | 09/12/2021 | 08/01/2022 | PRADIP KUMAR JATI | 4.07 | 3.92 | 96.37 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000777/2020-2021 | 84434 | 01/03/2021 |  | DEV DAS SHAW | 27.09 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Retrofitting Khosalpur Water Supply Scheme |  |  | VCH/000869/2020-2021 | 84435 | 01/03/2021 |  | PRADIP KUMAR JATI | 24.12 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000871/2020-2021 | 844327 | 17/03/2021 |  | JAHANGIR ALAM | 26.44 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000873/2020-2021 | 844330 | 17/03/2021 |  | M/S ASHIRBAD (INDIA) | 27.58 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Additional Retrofitting Khoshalpur |  |  | VCH/000927/2021-2022 | BP-2021-22-387 | 07/03/2022 |  | JAHANGIR ALAM | 3.45 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Additional Retrofitting Khoshalpur |  |  | VCH/000931/2021-2022 | BP-2021-22-385 | 08/03/2022 |  | JAHANGIR ALAM | 3.44 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme. |  |  | VCH/000952/2020-2021 | 8443106 | 30/03/2021 |  | NATURAL RESOURCES CONSORTIUM | 21.16 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (Phase-1) |  |  | VCH/001021/2021-2022 | BP-2021-22-451 | 25/03/2022 |  | N. G ENGINEERING | 3.11 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | SM/06785 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) |  |  | VCH/001027/2021-2022 | BP-2021-22-449 | 30/03/2022 |  | M/S ASHIRBAD (INDIA) | 4.52 | 0 | 0 | 0
Total | [13 empty] | 227.75 | 7.71 | 3.38