## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Kanpur Mouza (part) | AE/Ulu | JE/USD | ORD/000106/2020-2021 | 1340/HD | 13/10/2020 | 12/11/2020 | NATURAL RESOURCES CONSORTIUM | 28.42 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Kanpur Mouza (part) | AE/Ulu | JE/USD | ORD/000107/2020-2021 | 1341/HD | 13/10/2020 | 12/11/2020 | NATURAL RESOURCES CONSORTIUM | 28.2 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kanpur Mouza (part) | AE/Ulu |  | ORD/000419/2020-2021 | 93/HD | 14/01/2021 | 13/02/2021 | PIKASU BOSE | 21.97 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) (for Kanpur Mouza (part) | AE/Ulu |  | ORD/000420/2020-2021 | 94/HD | 14/01/2021 | 13/02/2021 | MAA LAXMI ENTERPRISE | 28.63 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kanpur Mouza (part) | AE/Ulu |  | ORD/000421/2020-2021 | 95/HD | 14/01/2021 | 13/02/2021 | PIKASU BOSE | 28.49 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-G) | AE/Ulu |  | ORD/000422/2020-2021 | 96/HD | 14/01/2021 | 13/02/2021 | PIKASU BOSE | 26.97 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme |  |  | VCH/000339/2021-2022 | W/255 | 03/09/2021 |  | PIKASU BOSE | 25.21 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting of Kanpur Reju Water Supply Scheme |  |  | VCH/000797/2020-2021 | 844321 | 12/03/2021 |  | NATURAL RESOURCES CONSORTIUM | 24.79 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme |  |  | VCH/000874/2020-2021 | 844342 | 17/03/2021 |  | MAA LAXMI ENTERPRISE | 21.27 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme |  |  | VCH/000879/2021-2022 | 844328 | 29/03/2022 |  | PIKASU BOSE | 3.17 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | SM/06786 | Retrofitting | Alternative relaying pipeline at Reju of Kanpur PWSS. |  |  | VCH/000900/2021-2022 | 844329 | 29/03/2022 |  | PIKASU BOSE | 2.87 | 0 | 0 | 0
Total | [13 empty] | 239.98 | 0 | 0