## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Surveying, Planning, Design, Delivery, Erection and Construction of Intake arrangement, WTP including inlet well , flash mixture Chemical House , Clariflocculator with sump , Rapid Gravity Filter with back washing system, sludge pond with sludge pumping system , CWR, OHR, Rising Main, Remodelling of Distribution System, Administrative Building, Sub-Station Building, Lab, Store ,Staff Quarters ,Boundary wall, Approach Road all complete including Mechanical/Electrical works both for raw water intake and treatment plant consisting of supply, installation, commissioning of pumping machineries, substation equipments etc inclusive of all kinds of accessories and ancillaries etc all complete along with 6 months trial run & 5(five) years operation and maintenance¿ for Surface Water Based Water Supply Scheme at Bally Jagacha Block, District ¿ Howrah |  |  | ORD/000002/2013-2014 | work Order-1697/HD | 06/11/2013 |  | GANNON DUNKERLEY & CO. LTD. | 25.83 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Work Order for Riverine effect over Construction of 400 m3 capacity and 20 mtr staging height RCC Over Head Reservoir including pile foundation & delivery inlet & outlet and overflow pipe connection and allied works as per departmental drawing (DRG No. ¿ PC-I/OHR/11/2012) at Chitnan water supply scheme under Uluberia Sub-Division, under Howrah Division PHE Dte | AE/Ulu | JE/USD | ORD/000395/2021-2022 | 160/HD | 25/01/2022 | 11/03/2022 | S.N ENTERPRISE | 4.55 | 4.55 | 100 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) [Beral Mouza] [Number of FHTC to be provided (Approx) : 387] | AE/Ulu | JE/USD | ORD/000396/2020-2021 | 45/HD | 05/01/2021 | 04/02/2021 | MS ASOKE GHOSH AND BROTHERS | 22.44 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Retrofitting Chitnan Water Supply Scheme |  |  | VCH/000005/2021-2022 | null | 19/04/2021 |  | JAHANGIR ALAM | 23.87 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Retrofitting Chitnan Water Supply Scheme |  |  | VCH/000006/2021-2022 | W/120 | 20/07/2021 |  | ASHOKE GHOSH AND BROTHERS | 15.46 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Retrofitting Chitnan Water Supply scheme |  |  | VCH/000023/2021-2022 | W/170 | 09/08/2021 |  | PRASANTA SANA | 19.78 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Retrofitting Chitnan |  |  | VCH/000038/2021-2022 | W/171 | 09/08/2021 |  | BOSE AND CO. | 26.83 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Retrofitting Chitnan |  |  | VCH/000039/2021-2022 | null | 03/06/2021 |  | S.N ENTERPRISE | 26.88 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Work Order for Riverine effect over Construction of 400 m3 capacity and 20 mtr staging height RCC Over Head Reservoir including pile foundation & delivery inlet & outlet and overflow pipe connection and allied works as per departmental drawing (DRG No. ¿ PC-I/OHR/11/2012) at Chitnan water supply scheme under Uluberia Sub-Division, under Howrah Division PHE Dte |  |  | VCH/000348/2022-2023 | null | 20/07/2022 |  | S.N ENTERPRISE | 3.52 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Construction of Bounadry wall Chitnan Water supply scheme |  |  | VCH/000405/2022-2023 | BP-2022-23-71 | 14/06/2022 |  | M/S SARADA UDYOG | 2.14 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Construction of 28 nos stand post at in various place of Chitnan Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-II) |  |  | VCH/000802/2021-2022 | BP-2021-22-338 | 17/02/2022 |  | ANUP PAUL | 2.63 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Construction of 35 nos stand post at in various place of Chitnan Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-I) |  |  | VCH/000803/2021-2022 | BP-2021-22-339 | 17/02/2022 |  | ANUP PAUL | 3.28 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | SM/07395 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) [Mirgram Mouza] [Number of FHTC to be provided (Approx) : 415] |  |  | VCH/001010/2021-2022 | BP-2021-22-472 | 30/03/2022 |  | PRASANTA SANA | 4.79 | 0 | 0 | 0
Total | [13 empty] | 181.98 | 4.55 | 2.5