## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II | SM/07464 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A)[Dakshin Jaypur Mouza] [Number of FHTC to be provided (Approx) : 227] | AE/Ulu | JE/USD | ORD/000391/2020-2021 | 46/HD | 05/01/2021 | 04/02/2021 | MAHARAJ CONSTRUCTION CO | 14.33 | 11.81 | 82.44 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II | SM/07464 | Retrofitting | Retrofitting Joypur |  |  | VCH/000050/2021-2022 | W/154 | 09/08/2021 |  | N. G ENGINEERING | 37.09 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II | SM/07464 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) [Jaypur Mouza part] [Number of FHTC to be provided (Approx) : 650] |  |  | VCH/000923/2021-2022 | BP-2021-22-378 | 03/03/2022 |  | M/S ASHIRBAD (INDIA) | 39.42 | 0 | 0 | 0
Total | [13 empty] | 90.83 | 11.81 | 13.01