## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | SM/07886 | Retrofitting | Withdrawing and re-laying of UPVC pipeline damaged due to irrigation embarkment protection work at section 118-117-115-114-113-147-145-148 in Sehagori Water Supply Scheme(Part-B) under Amta-II block under Howrah Division , PHE Dte. (SL NO.-2 ) | AE/Ulu |  | ORD/000312/2022-2023 | 373/AE/USD | 30/08/2022 | 14/10/2022 | PRADIP KUMAR JATI | 4.85 | 4.84 | 99.73 | 100
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | SM/07886 | Retrofitting | Work order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. for 2721 | AE/Ulu | JE/USD | ORD/000375/2021-2022 | 87/HD | 14/01/2022 | 28/02/2022 | PRADIP KUMAR JATI | 114.31 | 19.43 | 17 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | SM/07886 | Retrofitting | Work order for Additional pipeline laying for left out portion (naba santra, ganesh santra, judhistir khanra, sourav khanra's house, Vai Vai milan sangha, kabir roy, avijit roy, Ashoke roy, kashinath middey) in Sehagori Water Supply Scheme (Part-A&B) under Amtra-II block under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000533/2021-2022 | 217/HD | 03/02/2022 | 20/03/2022 | PRADIP KUMAR JATI | 4.84 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | SM/07886 | Retrofitting | Work Order for Additional pipeline laying for left out portion (Sibu house to burning ghat, Sk sifuddin to Sabir mollah, Sala Mudi shop to Moti mallick, Sk Faire to Sk Faiul, Das's Badh to Saidul mir, , indian petrol pump, dey builder, sikha dey, rajkumar mondal, porimal santra) in Sehagori Water Supply Scheme (Part-B) under Amtra-II block under Howrah Division, PHE Dte. (Phase-I) | AE/Ulu | JE/USD | ORD/000534/2021-2022 | 229/HD | 03/02/2022 | 20/03/2022 | PRADIP KUMAR JATI | 4.82 | 4.69 | 97.15 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | SM/07886 | Retrofitting | Work order for Additional pipeline laying for left out portion (Tarun Sangha to Sanat roy, umbrella factory, sk para masjid to sk billu, sala modi shop, sova dolui, Bharat Petrolium, biswa mondal, haru dey, joydev dye, ibrahim mir, moonlight club) in Sehagori Water Supply Scheme (Part-B) under Amtra-II block under Howrah Division, PHE Dte. (Phase-II) | AE/Ulu | JE/USD | ORD/000535/2021-2022 | 230/HD | 03/02/2022 | 20/03/2022 | PRADIP KUMAR JATI | 4.84 | 4.79 | 98.85 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | SM/07886 | Retrofitting | Work Order for Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system at Sehagori W/S scheme under Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000770/2022-2023 | 737/HD | 23/02/2023 | 24/04/2023 | JHARNA ENTERPRISE | 19.04 | 19.04 | 99.99 | 40
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | SM/07886 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 495/HD | 07/03/2022 |  | Resource Division | 3.08 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | SM/07886 | Retrofitting | Work order for Additional pipeline laying for left out portion (naba santra, ganesh santra, judhistir khanra, sourav khanra's house, Vai Vai milan sangha, kabir roy, avijit roy, Ashoke roy, kashinath middey) in Sehagori Water Supply Scheme (Part-A&B) under Amtra-II block under Howrah Division, PHE Dte. |  |  | VCH/000841/2022-2023 | BP-2022-23-263 | 28/09/2022 |  | PRADIP KUMAR JATI | 4.06 | 0 | 0 | 0
Total | [13 empty] | 159.86 | 52.79 | 33.02