## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Bally Jagacha Phase -I |  |  | BILL/00155/2022-2023 | null | 20/01/2023 |  | EASTERN RAILWAY, HOWRAH DIVISION | 15.58 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Sample Test |  |  | BILL/00350/2022-2023 | null | 24/03/2023 |  | NATIONAL TEST HOUSE | 0.09 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | National Test House |  |  | BILL/00461/2022-2023 | BP-2022-23-691 | 16/03/2023 |  | NATIONAL TEST HOUSE | 0.09 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Railway Permission |  |  | BILL/00464/2022-2023 | BP-2022-23-624 | 30/03/2023 |  | EASTERN RAILWAY, HOWRAH DIVISION | 11.93 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Eastern Railway, Howrah Division |  |  | BILL/00465/2022-2023 | BP-2021-22-623 | 30/03/2023 |  | EASTERN RAILWAY, HOWRAH DIVISION | 1.11 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Surveying, Planning, Design, Delivery, Erection and Construction of Intake arrangement, WTP including inlet well , flash mixture Chemical House , Clariflocculator with sump , Rapid Gravity Filter with back washing system, sludge pond with sludge pumping system , CWR, OHR, Rising Main, Remodelling of Distribution System, Administrative Building, Sub-Station Building, Lab, Store ,Staff Quarters ,Boundary wall, Approach Road all complete including Mechanical/Electrical works both for raw water intake and treatment plant consisting of supply, installation, commissioning of pumping machineries, substation equipments etc inclusive of all kinds of accessories and ancillaries etc all complete along with 6 months trial run & 5(five) years operation and maintenance¿ for Surface Water Based Water Supply Scheme at Bally Jagacha Block, District ¿ Howrah |  |  | ORD/000002/2013-2014 | work Order-1697/HD | 06/11/2013 |  | GANNON DUNKERLEY & CO. LTD. | 25.83 | 40.93 | 158.45 | 0
7 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Remaining part of laying distribution system of Pipe water supply at Zone-III/IV.(pal para,mondal para, kote para, Rupnagar)for Surface water based water supply project for Bally-Jagacha(PH-II), under Howrah Division, PHE Dte.(Part-B). |  | JE Sadar | ORD/000009/2022-2023 | 817/HD | 08/04/2022 | 08/05/2022 | M/S MOINAK POREL | 19.5 | 0 | 0 | 100
8 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/05/2024 to 31/07/2024) under Howrah Division, PHE Dte. | AE HQ |  | ORD/000009/2024-2025 | 2219/HD | 30/04/2024 | 29/07/2024 | SUMANTA DEY | 1 | 0.91 | 91.76 | 0
9 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Surveying, Planning, Design, Delivery, Erection and Construction of Intake arrangement, WTP including inlet well , flash mixture Chemical House , Clariflocculator with sump , Rapid Gravity Filter with back washing system, sludge pond with sludge pumping system , CWR, OHR, Rising Main, Remodelling of Distribution System, Administrative Building, Sub-Station Building, Lab, Store ,Staff Quarters ,Boundary wall, Approach Road all complete including Mechanical/Electrical works both for raw water intake and treatment plant consisting of supply, installation, commissioning of pumping machineries, substation equipmentsetc inclusive of all kinds of accessories and ancillaries etc all complete along with 6 months trial run & 5(five) years operation and maintenance¿ for Surface Water Based Water Supply Scheme at Bally Jagacha Block. |  |  | ORD/000010/2013-2014 | 1697/HD | 06/11/2013 | 04/11/2023 | GANNON DUNKERLEY & CO. LTD. | 1515.8 | 219.49 | 14.48 | 25
10 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Withdrawing & relaying distribution system pipe line from Makaltala to Bally station (N.P.- 155 to 4) in the uncovered areas of Surface water based water supply project for Bally Jagacha block, under Howrah Division PHE Dte.(D.A-1 G.P Area) Zone-5 Length= 1.05km.nos. | AE HQ |  | ORD/000010/2022-2023 | 818/HD | 08/04/2022 | 08/05/2022 | BISWAJIT SAMANTA | 7.94 | 7.25 | 91.32 | 100
11 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Surveying, Planning, Design, Delivery, Erection and Construction of Intake arrangement, WTP including inlet well , flash mixture Chemical House , Clariflocculator with sump , Rapid Gravity Filter with back washing system, sludge pond with sludge pumping system , CWR, OHR, Rising Main, Remodelling of Distribution System, Administrative Building, Sub-Station Building, Lab, Store ,Staff Quarters ,Boundary wall, Approach Road all complete including Mechanical/Electrical works both for raw water intake and treatment plant consisting of supply, installation, commissioning of pumping machineries, substation equipmentsetc inclusive of all kinds of accessories and ancillaries etc all complete along with 6 months trial run & 5(five) years operation and maintenance¿ for Surface Water Based Water Supply Scheme at Bally JagachaBlock. |  |  | ORD/000011/2013-2014 | 1697/HD | 06/11/2013 |  | GANNON DUNKERLEY & CO. LTD. | 275.59 | 61.67 | 22.38 | 0
12 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/06/2024 to 31/07/2024) | AE HQ | je2_how | ORD/000011/2024-2025 | 2566/HD | 30/05/2024 | 30/07/2024 | AVINABA ENGINEERING CONCERN | 0.79 | 0.78 | 98.67 | 0
13 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Nischinda Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-A) No. of House Hold(Approx)=4500 nos. | AE HQ |  | ORD/000031/2021-2022 | 1310/HD | 24/06/2021 | 08/08/2021 | JDJ ENTERPRISE A UNIT OF JDJ TRADERS PRIVATE LIMITED | 198.75 | 68.97 | 34.7 | 0
14 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. | AE HQ |  | ORD/000032/2021-2022 | 1311/HD | 24/06/2021 | 08/08/2021 | JAYANTA KUMAR MONDAL | 239.97 | 204.66 | 85.28 | 0
15 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. | AE HQ |  | ORD/000033/2021-2022 | 1312/HD | 24/06/2021 | 08/08/2021 | GHOSH CONCERN | 176.91 | 12.56 | 7.1 | 0
16 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-2. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold(Approx)= 4500 nos | AE HQ |  | ORD/000034/2021-2022 | 1313/HD | 24/06/2021 | 08/08/2021 | ALOK ENTERPRISE | 232 | 37.12 | 16 | 0
17 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chakpara Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold(Approx)=5000 nos. | AE HQ |  | ORD/000035/2021-2022 | 1314/HD | 24/06/2021 | 08/08/2021 | MAHAVIR PUMPS MFG.PVT.LTD | 220.68 | 108.75 | 49.28 | 100
18 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface Based Water Supply Project for Bally-Jagacha Block, under HowrahDivision,PHEDte. (D.A-1G.PArea) Zone-5 | AE HQ |  | ORD/000035/2023-2024 | 1707/HD | 24/04/2023 | 04/05/2023 | S.B. ENTERPRISE | 0.88 | 0.42 | 48.17 | 100
19 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Jagadispur Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-G) No. of House Hold(Approx)= 3500 nos. | AE HQ |  | ORD/000036/2021-2022 | 1315/HD | 24/06/2021 | 08/08/2021 | VISHAL CONSTRUCTION CO. | 176.21 | 159.44 | 90.48 | 0
20 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Carrying charges office CE Office (HQ) NS Building to Bally WTP Site & WTP Site to Howrah Division office under Howrah Division, PHE Dte. | AE HQ |  | ORD/000036/2023-2024 | 1708/HD | 24/04/2023 | 01/05/2023 | MENOKA ENGINEERING WORKS | 0.82 | 0.41 | 49.65 | 100
21 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying Distribution Pipeline For Uncovered area at Zone-IV of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | AE HQ |  | ORD/000043/2024-2025 | 2892/HD | 26/06/2024 | 25/08/2024 | S.B ENTERPRISE | 18.4 | 0 | 0 | 0
22 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Restoration of road in uncovered areas in Zone-1 & 2. under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. Howrah Length- 750m. (Part-I) |  |  | ORD/000054/2021-2022 | 1368/HD | 29/06/2021 | 29/07/2021 | SK ENTERPRISE | 4.33 | 3.42 | 78.94 | 0
23 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/07/2024 to 30/09/2024) under Howrah Division, PHE Dte. | AE HQ,Assistant Engineer/IU III | je2_pdd1 | ORD/000060/2024-2025 | 2924/HD | 27/06/2024 | 27/09/2024 | MD KADIR | 1 | 0.96 | 96.78 | 0
24 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Dismantling of concrete road for laying of pipe line in Zone-4 under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division, PHE Dte. (Part-A) | AE HQ |  | ORD/000081/2022-2023 | 1139/HD | 27/05/2022 | 16/06/2022 | A.G.S ENTERPRISE | 3.93 | 0 | 0 | 0
25 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Dismantling of concrete road for laying of pipe line in Zone-4 under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division, PHE Dte. (Part-B) | AE HQ |  | ORD/000082/2022-2023 | 1140/HD | 27/05/2022 | 16/06/2022 | A.G.S ENTERPRISE | 3.75 | 0 | 0 | 0
26 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Adopting Jack Pushing of 813 mm Dia 10 mm thick M.S pipe as Casing to Cross Water carrier Pipe on Tentulkuli rail crossing work of Bally Jagacha (PH-II) Surface Water Supply Scheme under Howrah Division P.H.E. Dte. | AE HQ |  | ORD/000082/2023-2024 | 1963/HD | 11/05/2023 | 25/06/2023 | SUBHASH BOSE | 95.69 | 47.84 | 50 | 100
27 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Construction of Retaining Wall at Narna Zone-V OHR Site under Bally Jagacha(phase-II) surface Based water supply project under Howrah Division, P.H.E. Dte. | AE HQ |  | ORD/000085/2024-2025 | 3463/HD | 02/08/2024 | 01/09/2024 | GUPTA ENTERPRISE | 4.76 | 0 | 0 | 0
28 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Construction of partition wall and Earth filling in passage at Narna Zone-V OHR Site under Bally Jagacha(phase-II) surface Based water supply project under Howrah Division, P.H.E. Dte. | AE HQ |  | ORD/000086/2024-2025 | 3464/HD | 02/08/2024 | 01/09/2024 | GUPTA ENTERPRISE | 4.48 | 0 | 0 | 0
29 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Special repairing for Distribution system and brusting of rising main at Lakshmanpur, Jotgiri & Narna of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | AE HQ |  | ORD/000087/2024-2025 | 3465/HD | 02/08/2024 | 17/08/2024 | COSMO ENTERPRISE | 3.91 | 0 | 0 | 0
30 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/08/2024 to 30/09/2024) | AE HQ | je2_how | ORD/000088/2024-2025 | 3362/HD | 30/07/2024 | 29/09/2024 | AVINABA ENGINEERING CONCERN | 0.79 | 0.39 | 49.71 | 0
31 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/08/2024 to 31/10/2024) under Howrah Division, PHE Dte. | AE HQ |  | ORD/000089/2024-2025 | 3379/HD | 30/07/2024 | 30/10/2024 | SUMANTA DEY | 1 | 0.29 | 29.36 | 0
32 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for (i)Construction of 600 cum capacity, 20 mtr. staging height RCC Elevated Service Reservoir in terms with Departmental type design including soil testing & submission of design of pile foundation & delivery, inlet, outlet & overflow pipe connection all complete ii)Making By-pass arrangement of concerned OHR for the distribution system including supply of all materials as per requirement (Zone-VI), (iii)Land development including pathway at OHR Site [Zone-VI] and iv)Laying distribution system of (Zone-IV, Part-C) and v)Construction of Boundary wall for (Zone-VI) and vi)Construction of Guard Room (Zone-VI) for ¿Surface water based water supply scheme for Bally-Jagachha (Phase-II) District Howrah under Howrah Division, P.H.E. Dte. |  |  | ORD/000126/2019-2020 | 987/HD | 01/07/2019 | 26/04/2020 | GHOSH CONCERN | 183 | 0.26 | 0.14 | 100
33 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Construction of clear water reservoir at WTP Site of 3600 cum capacity for Surface Water Based Water Supply Scheme Bally Jagacha Phase-II |  |  | ORD/000145/2018-2019 | 1554/HD. | 04/10/2018 | 03/10/2023 | SAMIRON GHOSH | 932.47 | 9.56 | 1.03 | 100
34 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | 1. Clear water rising main from GLR to different Zonal OHR, 2. Laying distribution system of piped water supply at (Zone-VI) and 3. Construction of Administrative Building, Store & Stack Yard at Domjur Boosting Station for surface water based water supply scheme for Bally-Jagacha (Phase-II) under Howrah Division, P.H.E. Dte. |  | JE Sadar | ORD/000151/2020-2021 | 1597/HD | 09/11/2020 | 03/05/2022 | SUBHASH BOSE | 267 | 13.78 | 5.16 | 50
35 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Special repairing works in different location( at Lock down period) in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Nischinda G.P Area) Zone-6A, 6B. | AE HQ |  | ORD/000181/2020-2021 | 1172/HD | 30/09/2020 | 30/10/2020 | MENOKA ENGINEERING WORKS | 1.77 | 1.27 | 71.81 | 0
36 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara Basukati G.P Area) Zone-7,8 Length= 736.00mtr.(PART-J) | AE HQ |  | ORD/000188/2020-2021 | 1179/HD | 30/09/2020 | 30/10/2020 | NIRMAL UDYOG | 4.5 | 1.76 | 39.12 | 0
37 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Sinking of 2 (two) nos PVC big dia Tube well 300 mm x 200 mm dia of 240 mtr deep near i)Bally Ghosh Para OHR Site Zone-6A & ii)Jagadishpur OHR Site Zone-14 under BallyJagacha Surface Based W/S scheme (Phase-I) under Howrah Division P.H.E Dte. | AE HQ | je2_pdd1 | ORD/000191/2022-2023 | 1596/HD | 01/08/2022 | 31/08/2022 | MUNSHI ENTERPRISE | 32.38 | 18.49 | 57.1 | 30
38 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Sinking of 2 (two) nos PVC big dia Tube well 300 mm x 200 mm dia of 240 mtr deep near i)Chamrail OHR Site Zone-13 & ii) Bally Jagacha Block Office OHR Site Zone-12 under Bally-Jagacha Surface Based W/S scheme(Phase-I) under Howrah Division P.H.E Dte. | AE HQ |  | ORD/000192/2022-2023 | 1597/HD | 01/08/2022 | 31/08/2022 | MUNSHI ENTERPRISE | 32.38 | 25.21 | 77.87 | 0
39 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Development of Road at Pakuria OHR in Zone-VI under Bally Jagacha (PH-II) Surface water supply scheme under Howrah Division, PHE Dte. | AE HQ |  | ORD/000228/2023-2024 | 2818/HD | 03/08/2023 | 18/08/2023 | M/S HOWRAH CONSTRUCTION | 0.88 | 0.43 | 49.14 | 100
40 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Land Development for Approach to OHR Site at Narna Zone-V of Surface water supply scheme Bally Jagacha (Phase-II) under Howrah Division, PHE Dte. | AE HQ |  | ORD/000229/2023-2024 | 2819/HD | 03/08/2023 | 18/08/2023 | GUPTA ENTERPRISE | 0.79 | 0 | 0 | 0
41 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for two months from 01/09/2023 to 31/10/2023) under Howrah Division, PHE Dte.. | Assistant Engineer/IU III |  | ORD/000231/2023-2024 | 3134/HD | 29/08/2023 | 29/10/2023 | INDRAJIT GHOSAL | 0.8 | 0.41 | 51.95 | 30
42 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface Water Based Project for Bally-Jagacha block under Howrah Division, PHE Dte (Chakpara, G.P. Area) Zone-10 Length=900.00mtr. | AE HQ |  | ORD/000288/2021-2022 | 2272/HD | 10/12/2021 | 09/01/2022 | USHA CONCERN | 4.13 | 0.91 | 21.96 | 0
43 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Working area Development for Administrative Building (At Salap Zone-VII) for Surface Water Based Water Supply Scheme Bally Jagacha (Phase-II) under Howrah Division, PHE Dte. | AE HQ |  | ORD/000292/2021-2022 | 2276/HD | 10/12/2021 | 31/12/2021 | KRISHNA CONSTRUCTION | 3.14 | 3.13 | 99.63 | 0
44 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation Order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme Government of West Bengal (for two months from 01/11/2023 to 31/12/2023) under Howrah Division, PHE Dte.. | Assistant Engineer/IU III |  | ORD/000296/2023-2024 | 3902/HD | 30/10/2023 | 30/12/2023 | INDRAJIT GHOSAL | 0.8 | 0.26 | 32.62 | 50
45 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte.(Part-A) No. of House Hold= 110 nos. | AE HQ |  | ORD/000313/2021-2022 | 2280/HD | 10/12/2021 | 09/01/2022 | N. G ENGINEERING | 4.76 | 4.64 | 97.68 | 0
46 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying of Distribution system at uncovered areas of Pipli & Gayespur mouza under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. | AE HQ | je_blk_ballyjag_how | ORD/000313/2023-2024 | 4363/HD | 05/12/2023 | 19/01/2024 | SAIKAT ENTERPRISE | 14.52 | 5.21 | 35.9 | 60
47 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold= 110 nos. | AE HQ |  | ORD/000314/2021-2022 | 2281/HD | 10/12/2021 | 09/01/2022 | M/S ASHIRBAD (INDIA) | 4.76 | 4.65 | 97.81 | 0
48 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold= 110 nos. | AE HQ |  | ORD/000315/2021-2022 | 2282/HD | 10/12/2021 | 09/01/2022 | S.B. ENTERPRISE | 4.74 | 4.63 | 97.67 | 0
49 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold= 110 nos. | AE HQ |  | ORD/000316/2021-2022 | 2283/HD | 10/12/2021 | 09/01/2022 | APEX ENGINEERING | 4.74 | 4.67 | 98.55 | 0
50 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-E) No. of House Hold= 110 nos. | AE HQ |  | ORD/000317/2021-2022 | 2284/HD | 10/12/2021 | 09/01/2022 | DEBABRATA CHAKRABORTY | 4.74 | 4.53 | 95.72 | 0
51 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold= 110 nos. | AE HQ |  | ORD/000318/2021-2022 | 2285/HD | 10/12/2021 | 09/01/2022 | SUNIL ENTERPRISE | 4.74 | 4.54 | 95.71 | 0
52 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-G) No. of House Hold= 110 nos. | AE HQ |  | ORD/000319/2021-2022 | 2286/HD | 10/12/2021 | 09/01/2022 | GHOSH ENTERPRISE. | 4.78 | 4.63 | 96.69 | 0
53 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying of Distribution system at uncovered areas of Daffarpur mouza(part no-18/19) under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. | AE HQ | Junior Engineer | ORD/000321/2023-2024 | 4437/HD | 08/12/2023 | 07/01/2024 | USHA CONCERN | 12.51 | 5.17 | 41.35 | 100
54 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying of Distribution system at Narna mouza under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. | AE HQ | JE Sadar | ORD/000329/2023-2024 | 4468/HD | 12/12/2023 | 11/01/2024 | PBA INFRASTRUCTURE | 11.44 | 0 | 0 | 0
55 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying of Distribution system for uncovered areas at Boluhati mouza(Booth no-7,8,9), under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. | AE HQ | Junior Engineer | ORD/000341/2023-2024 | 4577/HD | 18/12/2023 | 17/01/2024 | CONSTRUCTION CORNER | 10.25 | 0 | 0 | 0
56 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Jagadispur Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No of House hold-1600 Nos | AE HQ |  | ORD/000351/2021-2022 | 2429/HD | 29/12/2021 | 12/02/2022 | N. G ENGINEERING | 54.6 | 51.86 | 95 | 0
57 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Nischinda Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-A) No of Household (Approx)= 4500 nos | AE HQ |  | ORD/000357/2021-2022 | 2384/HD | 27/12/2021 | 26/01/2022 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 2.24 | 2.06 | 91.93 | 0
58 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Sapuipara Basukati Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-B) No of Household (Approx)= 5500 nos | AE HQ |  | ORD/000358/2021-2022 | 2385/HD | 27/12/2021 | 26/01/2022 | JAYANTA KUMAR MONDAL | 2.73 | 0 | 0 | 0
59 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Duegapur-Abhoynagar-I Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-C) No of Household (Approx)= 4000 nos | AE HQ |  | ORD/000359/2021-2022 | 2386/HD | 27/12/2021 | 26/01/2022 | GHOSH CONCERN | 1.98 | 0 | 0 | 100
60 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Duegapur-Abhoynagar-II Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-D) No of Household (Approx)= 4500 nos | AE HQ |  | ORD/000360/2021-2022 | 2387/HD | 27/12/2021 | 26/01/2022 | ALOK ENTERPRISE | 2.24 | 1.4 | 62.62 | 0
61 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for the period from 01/10/2023 to 30/11/2023) | AE HQ |  | ORD/000360/2023-2024 | 3482/HD | 29/09/2023 | 29/11/2023 | SUMANTA DEY | 0.79 | 0.26 | 32.56 | 100
62 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Bally Gram Panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No. of House Hold= 5000 nos. | AE HQ |  | ORD/000361/2021-2022 | 57/HD | 10/01/2022 | 09/06/2022 | N. G ENGINEERING | 167.83 | 62.04 | 36.97 | 0
63 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chakpara Anandanagar Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-F) No of Household (Approx)= 5000 nos | AE HQ |  | ORD/000362/2021-2022 | 2388/HD | 27/12/2021 | 26/01/2022 | MAHAVIR PUMPS MFG.PVT.LTD | 2.48 | 2.48 | 100 | 0
64 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Jagadishpur Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-G) No of Household (Approx)= 3500 nos | AE HQ |  | ORD/000363/2021-2022 | 2389/HD | 27/12/2021 | 26/01/2022 | VISHAL CONSTRUCTION CO. | 1.74 | 1.74 | 100 | 0
65 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-1) No of Household (Approx)= 850 nos | AE HQ |  | ORD/000364/2021-2022 | 2390/HD | 27/12/2021 | 26/01/2022 | M/S ASHIRBAD (INDIA) | 0.42 | 0.42 | 100 | 0
66 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-2) No of Household (Approx)= 850 nos | AE HQ |  | ORD/000365/2021-2022 | 2391/HD | 27/12/2021 | 26/01/2022 | S.B. ENTERPRISE | 0.42 | 0.42 | 100 | 0
67 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-3) No of Household (Approx)= 850 nos | AE HQ |  | ORD/000366/2021-2022 | 2392/HD | 27/12/2021 | 26/01/2022 | N. G ENGINEERING | 0.42 | 0.42 | 100 | 0
68 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-4) No of Household (Approx)= 950 nos | AE HQ |  | ORD/000367/2021-2022 | 2393/HD | 27/12/2021 | 26/01/2022 | GHOSH ENTERPRISE. | 0.47 | 0.47 | 100 | 0
69 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Excavation of Pipe Trenches in different location for Testing of Rising main pipe line under Bally Jagacha (PH-I) Water supply Project in Bally Jagacha Block under Howrah Sadar Sub- Division, P.H.E. Dte. | AE HQ |  | ORD/000368/2022-2023 | 1869/HD | 12/09/2022 | 22/09/2022 | S.B. ENTERPRISE | 2.39 | 2.01 | 83.9 | 0
70 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Restoration of road damaged for providing FHTC Works in Nischinda G.P in Bally Jagacha Block under Howrah Division, PHE Dte. (Part-C) | AE HQ |  | ORD/000371/2022-2023 | 1891/HD | 15/09/2022 | 25/09/2022 | M/S HOWRAH CONSTRUCTION | 4.53 | 4.33 | 95.5 | 0
71 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara. G.P Area) Zone-10 Length= 539.00mtr.(PART-C) |  |  | ORD/000377/2020-2021 | 1104/HD | 25/09/2020 | 25/10/2020 | PRADIP KUMAR JATI | 4.04 | 0 | 0 | 0
72 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(D.A -2. G.P Area) Zone-1. Length= 55.00 mtr. | AE HQ |  | ORD/000379/2022-2023 | 1867/H.D | 12/09/2022 | 22/09/2022 | SKYLINE CONSTRUCTION | 0.48 | 0.4 | 83.05 | 0
73 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (from 01/01/2024 to 31/03/2024) under Howrah Division, PHE Dte. | Assistant Engineer/IU III |  | ORD/000412/2023-2024 | 4765/HD | 29/12/2023 | 29/03/2024 | INDRAJIT GHOSAL | 0.98 | 0.54 | 54.61 | 50
74 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for the period from 01/12/2023 to 31/01/2024) | AE HQ |  | ORD/000455/2023-2024 | 4303/HD | 30/11/2023 | 31/01/2024 | SUMANTA DEY | 0.79 | 0.31 | 39.49 | 100
75 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Construction of MS Pipe Line at Lakshmanpur Boosting Station Site under Bally Jagacha Surface Based Water Supply Project (Phase-II) under Howrah Division, PHE Dte. | AE HQ |  | ORD/000466/2021-2022 | 306/HD | 15/02/2022 | 07/03/2022 | GHOSH ENTERPRISE. | 3.05 | 0 | 0 | 0
76 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Detail study of existing Bally Jagacha Surface Based Water Supply Scheme (Phase-1) to develop Innovative Sustainable Solutions which are field relevant and address the challenges faced by the consumer, under Howrah Division, PHE Dte. | AE HQ |  | ORD/000480/2022-2023 | 2211/HD | 02/11/2022 | 31/01/2023 | AJIVAM WATER PRIVATE | 34.09 | 34.09 | 100 | 100
77 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Withdrawing & relaying in the damaged part of pipeline for extension of Saorapotakhal(From Anandanagar sitala tala to Jhautala more) at Chakpara Anandanagar G.P. areas of Surface water based water supply project for Bally-Jagacha block,(Phase-1) under Howrah Division PHE Dte. Zone-9( N.P-197 to 15) Length= 1600.00mtr. | AE/SADAR |  | ORD/000481/2021-2022 | 476/HD | 04/03/2022 | 18/04/2022 | S.B. ENTERPRISE | 15.39 | 5.57 | 36.17 | 0
78 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-I of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1300 m) (Part-6) |  |  | ORD/000515/2020-2021 | 334/HD | 05/02/2021 | 15/02/2021 | SK ENTERPRISE | 4.26 | 2.41 | 56.47 | 0
79 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-II of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1300 Mtr) (Part-3) |  |  | ORD/000522/2020-2021 | 341/HD | 05/02/2021 | 15/02/2021 | SK ENTERPRISE | 4.21 | 3.05 | 72.51 | 0
80 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-II of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1250Mtr) (Part-4) |  |  | ORD/000523/2020-2021 | 342/HD | 05/02/2021 | 15/02/2021 | SK ENTERPRISE | 4.05 | 3.3 | 81.41 | 0
81 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Supply of Materials at Lakshmanpur Boosting Station Site under Bally Jagacha Surface based water supply project (Phase-II) under Howrah Division, PHE Dte. | AE HQ |  | ORD/000547/2021-2022 | 698/HD | 24/03/2022 | 08/04/2022 | SK ENTERPRISE | 1.69 | 1.59 | 94.61 | 0
82 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Bally Jagacha Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000551/2023-2024 | 845/HD | 22/02/2024 | 08/03/2024 | M&M GRAPHICS | 2.04 | 2.04 | 100 | 100
83 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 440.00mtr.(PART-5)(Near Chakpara Market & Khal par) | AE HQ |  | ORD/000552/2021-2022 | 652/HD | 23/03/2022 | 22/04/2022 | BISWAJIT SAMANTA | 2.49 | 2.11 | 84.67 | 0
84 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 809.00mtr.(PART-1)(Near Burma colony) | AE HQ |  | ORD/000553/2021-2022 | 653/HD | 23/03/2022 | 22/04/2022 | PRADIP KUMAR JATI | 3.05 | 3.03 | 99.55 | 0
85 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 792.00mtr.(PART-2)(Near Chakpara Milony club) | AE HQ |  | ORD/000554/2021-2022 | 654/HD | 23/03/2022 | 22/04/2022 | PRADIP KUMAR JATI | 3.18 | 2.63 | 82.78 | 0
86 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 796.00mtr.(PART-3)(Near Anandanagar khal par) | AE HQ |  | ORD/000555/2021-2022 | 655/HD | 23/03/2022 | 22/04/2022 | MAA TARA CONSTRUCTION | 3.15 | 3.14 | 99.9 | 0
87 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 913.00mtr. (PART-4) | AE HQ |  | ORD/000556/2021-2022 | 656/HD | 23/03/2022 | 22/04/2022 | MAA TARA CONSTRUCTION | 2.94 | 2.92 | 99.35 | 0
88 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A & 7 Length= 715.00mtr.(PART-3)(Location Bally near 7no pole) | AE HQ |  | ORD/000557/2021-2022 | 657/HD | 23/03/2022 | 22/04/2022 | SAIKAT ENTERPRISE | 3.32 | 3.22 | 97.04 | 0
89 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. (Part-A) | AE HQ |  | ORD/000558/2020-2021 | 415/HD | 11/02/2021 | 26/02/2021 | MA TARA CONSTRUCTION | 4.68 | 2.42 | 51.6 | 0
90 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A & 7 Length= 385.00mtr.(PART-4)(Location Bally Ghosh para) | AE HQ |  | ORD/000558/2021-2022 | 658/HD | 23/03/2022 | 22/04/2022 | SAIKAT ENTERPRISE | 2.08 | 2.03 | 97.36 | 0
91 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. (Part-B) | AE HQ |  | ORD/000559/2020-2021 | 416/HD | 11/02/2021 | 26/02/2021 | GHOSH ENTERPRISE. | 4.5 | 3.7 | 82.09 | 0
92 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. |  |  | ORD/000561/2020-2021 | 418/HD | 11/02/2021 | 26/02/2021 | GHOSH ENTERPRISE. | 1.16 | 0.83 | 71.06 | 0
93 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Barbed wire fencing with angle for Boundary wall & 450mm dia Sluice valve chamber at Lakhanpur CWR site & Raghabpur site of Bally jagacha (phase-II) Surface based water supply scheme under Howrah Division P.H.E. Dte. | AE HQ |  | ORD/000570/2020-2021 | 541/HD | 25/02/2021 | 27/03/2021 | SK ENTERPRISE | 3.56 | 0.76 | 21.39 | 0
94 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Measuring water flow of pipe under the ground level by portable flow meter (Endress & Hauser make) after thorough cleaning the outer surface of the pipe line and installing the measuring device as per manufacturer¿s procedure including mobilization of portable flow meter by hired vehicle at point to point engaging skilled technician and labours for pipe line size up to 400mm diameter. | AE HQ |  | ORD/000573/2022-2023 | 2009/HD | 27/09/2022 | 12/10/2022 | EASTERN INDIA SALES & SERVICE | 1.26 | 1.26 | 100 | 0
95 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Measuring water flow of pipe under the ground level by portable flow meter (Endress & Hauser make) after thorough cleaning the outer surface of the pipe line and installing the measuring device as per manufacturer¿s procedure including mobilization of portable flow meter by hired vehicle at point to point engaging skilled technician and labours for pipe line size up to 450mm to 900mm diameter. | AE HQ |  | ORD/000574/2022-2023 | 2054/HD | 28/09/2022 | 13/10/2022 | EASTERN INDIA SALES & SERVICE | 0.28 | 0.28 | 100 | 0
96 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/02/2024 to 30/04/2024).¿ under Howrah Division, PHE Dte. | AE HQ |  | ORD/000597/2023-2024 | 421/HD | 31/01/2024 | 30/04/2024 | SUMANTA DEY | 1 | 0.72 | 72.2 | 20
97 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying Distribution Pipeline For Uncovered area at Zone-VII (Salap-2 GP) of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how,JE Sadar | ORD/000603/2023-2024 | 1133/HD | 06/03/2024 | 05/05/2024 | UNIVERSAL CONSTRUCTION | 38.43 | 14.61 | 38.01 | 90
98 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying Distribution Pipeline For Uncovered area at Lakshmanpur (Zone-I) of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000621/2023-2024 | 1154/HD | 07/03/2024 | 21/04/2024 | SAIKAT ENTERPRISE | 31.53 | 13.81 | 43.81 | 90
99 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 660.00mtr.(PART-4) |  |  | ORD/000654/2020-2021 | 513/HD | 25/02/2021 | 27/03/2021 | MENOKA ENGINEERING WORKS | 3.65 | 2.41 | 66.07 | 0
100 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying Distribution Pipeline For Uncovered area at Jotgiri (Zone-I) of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000654/2023-2024 | 1244/HD | 12/03/2024 | 26/04/2024 | COSMO ENTERPRISE | 28.36 | 10.35 | 36.49 | 0
101 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 649.00mtr.(PART-5) |  |  | ORD/000655/2020-2021 | 514/HD | 25/02/2021 | 27/03/2021 | MENOKA ENGINEERING WORKS | 3.51 | 2.37 | 67.68 | 0
102 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/02/2024 to 31/03/2024) | AE HQ | je2_how | ORD/000655/2023-2024 | 420/HD | 31/01/2024 | 31/03/2024 | AVINABA ENGINEERING CONCERN | 0.79 | 0.73 | 91.35 | 0
103 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 732.00mtr.(PART-6) |  |  | ORD/000656/2020-2021 | 515/HD | 25/02/2021 | 27/03/2021 | MENOKA ENGINEERING WORKS | 4.22 | 2.62 | 62.05 | 0
104 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Restoration of damaged concrete roads due to laying of pipe line at Salap 1 & 2 GP of Bally-Jagacha surface based water supply scheme Phase-II under Howrah Division PHE Dte. (Part-B). | AE HQ | je_blk_ballyjag_how,Junior Engineer | ORD/000665/2023-2024 | 1316/HD | 14/03/2024 | 13/05/2024 | BISWAJIT SAMANTA | 11.22 | 0 | 0 | 0
105 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/04/2024 to 31/05/2024) | AE HQ | je2_how | ORD/000724/2023-2024 | 1672/HD | 28/03/2024 | 28/05/2024 | AVINABA ENGINEERING CONCERN | 0.79 | 0.76 | 96.29 | 0
106 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/04/2024 to 30/06/2024) under Howrah Division, PHE Dte. | AE HQ,Assistant Engineer/IU III | je2_pdd1 | ORD/000725/2023-2024 | 1363/HD | 15/03/2024 | 14/06/2024 | MD KADIR | 0.99 | 0.96 | 96.49 | 0
107 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Interconnection from Existing Tube well to Distribution line at Baigachi (Zone-14) in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | AE HQ |  | ORD/000726/2022-2023 | 516/HD | 09/02/2023 | 11/03/2023 | SUNIL ENTERPRISE | 2.71 | 1.24 | 45.92 | 100
108 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Construction of Clorination Room ( 5.40m x 3.60 m) at Bhaskur Zone-III OHR Site under Bally jagacha(phase-2) surface Based water supply project under Howrah Division, P.H.E. Dte. at Lakhanpur CWR Site under Bally jagacha(phase-2) surface Based water supply project under Howrah Division, P.H.E. Dte. | AE HQ |  | ORD/000728/2022-2023 | 515/HD | 09/02/2023 | 10/04/2023 | KUNDU CONSTRUCTION | 6.16 | 5.82 | 94.54 | 100
109 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Construction of Boundary Wall at Tube Well Site of Chakpara Anandanagar Football Ground under Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte.(12M X12M) | AE HQ | je2_pdd1 | ORD/000732/2022-2023 | 569/HD | 13/02/2023 | 15/03/2023 | FUTURE CONSTRUCTION | 3.98 | 0 | 0 | 0
110 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Construction of Pump House (5.40m x 3.60 m) at Tube Well Site of Chakpara Anandanagar Football Ground under Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | Assistant Engineer/IU III | je2_pdd1 | ORD/000734/2022-2023 | 571/HD | 13/02/2023 | 14/04/2023 | MAITY CONSTRUCTIONS | 6.12 | 2.91 | 47.6 | 100
111 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Interconnection from Tube well to Bally jagacha OHR in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | AE HQ |  | ORD/000735/2022-2023 | 572/HD | 13/02/2023 | 15/03/2023 | MA-DURGA ENTERPRISE | 1.78 | 0.74 | 41.59 | 100
112 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Interconnection from Tube well to Distribution line at Chakpara site in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | AE HQ | je2_pdd1 | ORD/000736/2022-2023 | 573/HD | 13/02/2023 | 15/03/2023 | S.B. ENTERPRISE | 1.68 | 0 | 0 | 0
113 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Interconnection from Tube well to Jagadispur OHR in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. | AE HQ |  | ORD/000737/2022-2023 | 574/HD | 13/02/2023 | 15/03/2023 | S.B. ENTERPRISE | 2.2 | 1.27 | 57.73 | 100
114 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system at uncovered areas of Durgapur Abhoynagar-1 & 2 Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte.(Part-1) | AE HQ | je1_iu | ORD/000821/2022-2023 | 1050/HD | 15/03/2023 | 13/06/2023 | M/S SUPROVAT GHOSH | 6.79 | 4.34 | 63.95 | 100
115 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Work Order for providing Functional Household Tap Connection(FHTC) from existing distribution system at uncovered areas of Durgapur Abhoynagar-1 & 2 Gram Panchyet under bally Jagachha Block under Howrah Division, PHE Dte.(Part-2) | AE HQ,Assistant Engineer/IU III | je1_iu | ORD/000822/2022-2023 | 1051/HD | 15/03/2023 | 14/05/2023 | SONAR BANGLA ENTERPRISE | 6.71 | 2.14 | 31.94 | 70
116 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 3594/HD | 13/08/2024 |  | Resource Division | 5.64 | 0 | 0 | 0
117 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 2375/HD | 24/12/2021 |  | Resource Division | 16.5 | 0 | 0 | 0
118 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 435/HD | 28/02/2022 |  | Resource Division | 21.45 | 0 | 0 | 0
119 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2113/HD | 09/11/2022 |  | Resource Division | 61.6 | 0 | 0 | 0
120 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 134/HD | 10/01/2024 |  | Resource Division | 12.94 | 0 | 0 | 0
121 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 467/HD | 02/02/2024 |  | Resource Division | 5.18 | 0 | 0 | 0
122 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 467/HD | 02/02/2024 |  | Resource Division | 2.19 | 0 | 0 | 0
123 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 467/HD | 02/02/2024 |  | Resource Division | 1.49 | 0 | 0 | 0
124 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000003/2021-2022 | W/104 | 19/07/2021 |  | SAIKAT ENTERPRISE | 3.49 | 0 | 0 | 0
125 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered araes of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000004/2021-2022 | W/106 | 19/07/2021 |  | SAIKAT ENTERPRISE | 3.84 | 0 | 0 | 0
126 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS of uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000007/2021-2022 | W/99-103 | 19/07/2021 |  | MITHU BUILDERS | 16.75 | 0 | 0 | 0
127 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Scheme Bally Jagacha Block |  |  | VCH/000012/2021-2022 | 107-111 113-117 | 20/07/2021 |  | ADITYA HAZRA | 25.5 | 0 | 0 | 0
128 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000013/2021-2022 | W/112 | 20/07/2021 |  | UNIVERSAL CONSTRUCTION | 3.89 | 0 | 0 | 0
129 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000014/2021-2022 | W/105 | 19/07/2021 |  | S.M. CONSTRUCTION | 3.39 | 0 | 0 | 0
130 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000015/2021-2022 | W/118, 119 | 19/07/2021 |  | N. G ENGINEERING | 5.52 | 0 | 0 | 0
131 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered area of Surface Water Based Water supply project for Bally Jagacha Block |  |  | VCH/000021/2021-2022 | W/133-136 | 09/08/2021 |  | NIRMAL UDYOG | 13.94 | 0 | 0 | 0
132 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS Uncovered area Surface Water Based Water supply Project Bally Jagacha Block |  |  | VCH/000027/2021-2022 | W/164 | 09/08/2021 |  | PRAGATI CONSTRUCTION & CO | 18.44 | 0 | 0 | 0
133 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS Uncovered Bally Jagacha Surface Water Based Water Supply Project Bally Jagacha block |  |  | VCH/000035/2021-2022 | W/149-153 | 09/08/2021 |  | S.B. ENTERPRISE | 12.29 | 0 | 0 | 0
134 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS Uncovered Bally Jagacha |  |  | VCH/000036/2021-2022 | null | 03/06/2021 |  | MAA TARA CONSTRUCTION | 16.77 | 0 | 0 | 0
135 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS uncovered Bally Jagacha |  |  | VCH/000037/2021-2022 | W/137-142 | 09/08/2021 |  | USHA CONCERN | 20.51 | 0 | 0 | 0
136 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Retrofitting Bally Jagacha |  |  | VCH/000052/2021-2022 | null | 28/06/2021 |  | S.B. ENTERPRISE | 12.29 | 0 | 0 | 0
137 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS Uncovered Bally Jagacha |  |  | VCH/000054/2021-2022 | W/143 | 09/08/2021 |  | PRADIP KUMAR JATI | 29.38 | 0 | 0 | 0
138 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Uncoverd Bally jagacha |  |  | VCH/000095/2021-2022 | W/250 | 19/08/2021 |  | ABONTICA ENTERPRISE | 3.22 | 0 | 0 | 0
139 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Uncovered bally jagcha |  |  | VCH/000096/2021-2022 | W/249 | 19/08/2021 |  | ABONTICA ENTERPRISE | 1.94 | 0 | 0 | 0
140 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Uncovered bally jagcha |  |  | VCH/000097/2021-2022 | W/251 | 19/08/2021 |  | ABONTICA ENTERPRISE | 1.59 | 0 | 0 | 0
141 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Uncovered bally jagcha |  |  | VCH/000098/2021-2022 | W/252 | 19/08/2021 |  | SUSHANTA MONDAL | 1.03 | 0 | 0 | 0
142 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Uncoverd Bally Jagcha |  |  | VCH/000233/2021-2022 | W/228 | 19/08/2021 |  | ASHOKE ENGINEERING WORKS | 4.47 | 0 | 0 | 0
143 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Uncoverd Bally Jagcha |  |  | VCH/000234/2021-2022 | W/229-233 | 19/08/2021 |  | SUSHANTA MONDAL | 7.82 | 0 | 0 | 0
144 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Uncovered Bally Jagach |  |  | VCH/000235/2021-2022 | W/159-160 | 19/08/2021 |  | MAA TARA CONSTRUCTION | 16.77 | 0 | 0 | 0
145 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Based Water Supply Project Bally Jagach Block |  |  | VCH/000255/2021-2022 | W/400 | 11/10/2021 |  | M/S. SREE HARI CONSTRUCTION | 3.33 | 0 | 0 | 0
146 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000256/2021-2022 | BP-2021-22-217 | 11/10/2021 |  | N.N. CONSTRUCTION | 3.54 | 0 | 0 | 0
147 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000257/2021-2022 | BP-2021-22-187 | 07/10/2021 |  | SAIKAT ENTERPRISE | 4.48 | 0 | 0 | 0
148 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000261/2021-2022 | W/362 | 07/10/2021 |  | GHOSH ENTERPRISE. | 4.8 | 0 | 0 | 0
149 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000262/2021-2022 | W/363 | 07/10/2021 |  | GHOSH ENTERPRISE. | 4.37 | 0 | 0 | 0
150 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000263/2021-2022 | W/364 | 07/10/2021 |  | GHOSH ENTERPRISE. | 4.83 | 0 | 0 | 0
151 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000264/2021-2022 | W/365 | 07/10/2021 |  | GHOSH ENTERPRISE. | 4.78 | 0 | 0 | 0
152 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000265/2021-2022 | W/366 | 07/10/2021 |  | GHOSH ENTERPRISE. | 4.81 | 0 | 0 | 0
153 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000266/2021-2022 | BP-2021-22-182 | 07/10/2021 |  | GHOSH ENTERPRISE. | 4.14 | 0 | 0 | 0
154 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000267/2021-2022 | W/368 | 07/10/2021 |  | MA TARA CONSTRUCTION | 4.81 | 0 | 0 | 0
155 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000268/2021-2022 | W/370 | 07/10/2021 |  | MA TARA CONSTRUCTION | 4.66 | 0 | 0 | 0
156 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000269/2021-2022 | BP-2021-22-184 | 07/10/2021 |  | SK ENTERPRISE | 2.21 | 0 | 0 | 0
157 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000270/2021-2022 | BP-2021-22-186 | 07/10/2021 |  | SK ENTERPRISE | 4.84 | 0 | 0 | 0
158 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Special repairing works in different location( at Lock down period) in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A, 6B.Length=66m. |  |  | VCH/000289/2022-2023 | BP-2022-23-31 | 11/05/2022 |  | CONSCORP | 0.48 | 0 | 0 | 0
159 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyetunder Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. |  |  | VCH/000293/2022-2023 | BP-2022-23-28 | 11/05/2022 |  | JAYANTA KUMAR MONDAL | 2.73 | 0 | 0 | 0
160 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Railway permission |  |  | VCH/000419/2022-2023 | BP-2022-23-84 | 23/06/2022 |  | EASTERN RAILWAY, HOWRAH DIVISION | 9.05 | 0 | 0 | 0
161 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Indent of materials |  |  | VCH/000594/2021-2022 | BP-2021-22-309 | 02/02/2022 |  | EXECUTIVE ENGINNER RESOURCES DIVISION | 36.59 | 0 | 0 | 0
162 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. |  |  | VCH/000791/2021-2022 | BP-2021-22-323 | 18/02/2022 |  | GHOSH CONCERN | 116.13 | 0 | 0 | 0
163 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 743.00mtr.(PART-3) |  |  | VCH/000804/2021-2022 | BP-2021-22-344 | 28/02/2022 |  | N. G ENGINEERING | 3.23 | 0 | 0 | 0
164 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 737.00mtr.(PART-2) |  |  | VCH/000805/2021-2022 | BP-2021-22-345 | 28/02/2022 |  | N. G ENGINEERING | 3.26 | 0 | 0 | 0
165 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-1) No. of House Hold= 850 nos. |  |  | VCH/000807/2021-2022 | BP-2021-22-348 | 28/02/2022 |  | MENOKA ENGINEERING WORKS | 34.94 | 0 | 0 | 0
166 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 743.00mtr.(PART-8) |  |  | VCH/000809/2021-2022 | BP-2021-22-342 | 28/02/2022 |  | M/S ASHIRBAD (INDIA) | 3.21 | 0 | 0 | 0
167 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 738.00mtr.(PART-9) |  |  | VCH/000810/2021-2022 | BP-2021-22-341 | 28/02/2022 |  | M/S ASHIRBAD (INDIA) | 3.52 | 0 | 0 | 0
168 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-4) No. of House Hold= 950 nos. |  |  | VCH/000811/2021-2022 | BP-2021-22-351 | 28/02/2022 |  | GHOSH ENTERPRISE. | 13.09 | 0 | 0 | 0
169 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-3) No. of House Hold= 850 nos |  |  | VCH/000822/2021-2022 | BP-2021-22-349 | 28/02/2022 |  | N. G ENGINEERING | 34.98 | 0 | 0 | 0
170 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-2. Grampanchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold(Approx)= 4500 nos |  |  | VCH/000823/2021-2022 | BP-2021-22-350 | 28/02/2022 |  | ALOK ENTERPRISE | 76.01 | 0 | 0 | 0
171 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Nischinda Gram panchyet under BallyJagachha Block under Howrah Division, PHE Dte. (Part-A) No. of House Hold(Approx)=4500 nos. |  |  | VCH/000824/2021-2022 | BP-2021-22-360 | 28/02/2022 |  | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 104.97 | 0 | 0 | 0
172 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-2) No. of House Hold= 850 nos. |  |  | VCH/000830/2021-2022 | BP-2021-22-347 | 28/02/2022 |  | M/S ASHIRBAD (INDIA) | 34.95 | 0 | 0 | 0
173 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyetunder Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. |  |  | VCH/000906/2021-2022 | W/796 | 03/03/2022 |  | JAYANTA KUMAR MONDAL | 24.79 | 0 | 0 | 0
174 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chakpara Gram panchyet under BallyJagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold(Approx)=5000 nos. |  |  | VCH/000909/2021-2022 | BP-2021-22-485 | 30/03/2022 |  | MAHAVIR PUMPS MFG.PVT.LTD | 10.99 | 0 | 0 | 0
175 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 732.00mtr. (PART-1) |  |  | VCH/000925/2021-2022 | BP-2021-22-346 | 03/03/2022 |  | N. G ENGINEERING | 3.43 | 0 | 0 | 0
176 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara G.P Area) Zone-7/8 Length= 1100.00mtr.(PART-2) |  |  | VCH/000942/2021-2022 | BP-2021-22-456 | 26/03/2022 |  | CHOWDHUARY & CO | 3.48 | 0 | 0 | 0
177 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara G.P Area) Zone-7/8 Length= 1100.00mtr.(PART-1) |  |  | VCH/000951/2021-2022 | BP-2021-22-455 | 26/03/2022 |  | CHOWDHUARY & CO | 3.51 | 0 | 0 | 0
178 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. |  |  | VCH/000978/2021-2022 | BP-2021-22-419 | 21/03/2022 |  | GHOSH CONCERN | 39.01 | 0 | 0 | 0
179 | HOWRAH |  | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | SM/08582 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Bally Gram Panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No. of House Hold= 5000 nos. |  |  | VCH/001009/2021-2022 | BP-2021-22-478 | 27/03/2022 |  | N. G ENGINEERING | 96.53 | 0 | 0 | 0
Total | [13 empty] | 6392.47 | 1373.79 | 21.49