## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Work Order for Additional Laying Distribution Pipeline & allied works of Pulgustia PWSS at J.Bpur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000065/2023-2024 | 1926/HD | 10/05/2023 | 09/07/2023 | GHOSH CONCERN | 65.53 | 47.75 | 72.86 | 50
2 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Work Order for Laying Distribution System, Rising main , FHTC (4559 nos), Construction of Pump House at OHR site (5.4mX3.6m ) with water supply & sanitary arrangement, 2 (Two) nos Construction of Pump House(3.6 mX3.0m) with water supply & sanitary arrangement, 2(Two) nos Boundary Wall (OHR & Other tubewell site), Construction of of 450 Cum OHR with 20 mtr Staging Height with pile foundation for Augumention of PULGUSTIA Water Supply Scheme of JAGABALLAVPUR Block under Howrah Division, PHE Dte. | AE/SADAR | JE Sadar | ORD/000183/2022-2023 | 1437/HD | 12/07/2022 | 03/01/2024 | GHOSH CONCERN | 474.21 | 416.79 | 87.89 | 30
3 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with 150 mm. dia. PVC. Strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Pulgustia PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000587/2023-2024 | 995/HD | 01/03/2024 | 31/03/2024 | ACME CONSTRUCTION | 14.58 | 0 | 0 | 100
4 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Construction of 1 (One) Nos.Pump House (5.40m x 3.60m), Construction of 1(One) nos. Boundary Wall and Tube Well connection with existing Laying Distribution System Network and Restoration Works of Road under Pulgustia Piped Water Supply Scheme Under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000601/2023-2024 | 1001/HD | 01/03/2024 | 30/04/2024 | SUNIRMAN ENTERPRISE | 51.76 | 0 | 0 | 80
5 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Work Order for Sinking of 2(Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Polgustia PWSS of Jagatballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000657/2022-2023 | 168/HD | 13/01/2023 | 27/02/2023 | B K ENTERPRISE | 34.7 | 33.4 | 96.27 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 1624/HD | 05/08/2022 |  | Resource Division | 34.87 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 2839/HD | 23/12/2022 |  | Resource Division | 28.08 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 |  | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Palgustia PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. |  |  | VCH/000959/2021-2022 | BP-2021-22-406 | 14/03/2022 |  | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 0 | 0 | 0
10 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Power connection of reorganization at Polgustia w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 100000104716 Reference ID- 860294676 SM Code- 10143 |  |  | BILL/00079/2024-2025 | 36 | 09/04/2024 |  | WBSEDCL | 0.5 | 0 | 0 | null
11 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Quotation money deposition for new service connection at Polgustia w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1007622375 Reference ID- 106532179 SM Code- 00343 |  |  | BILL/00151/2024-2025 | 56 | 12/04/2024 |  | WBSEDCL | 10.94 | 0 | 0 | null
12 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Poulgusthia (Replacement) water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000110/2022-2023 | 719/ED | 03/02/2023 | 04/05/2023 | A.G. ENTERPRISE | 21.49 | 19.13 | 89.02 | 0
13 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pulgustia | SM/10143 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Poulgusthia (Replacement) water supply scheme, T.W. No. III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000884/2023-2024 | 3457/ED | 11/08/2023 | 09/11/2023 | M/S G P ENTERPRISE | 10.76 | 10.46 | 97.26 | 90
Total | [13 empty] | 1264.3 | 527.53 | 41.73