## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Work Order for Construction Of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/06/2012) Including All pipe Connection Of Rudrapur PWSS In Domjur Block Of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000032/2023-2024 | 1740/HD | 25/04/2023 | 19/02/2024 | N. G ENGINEERING | 147.33 | 17.2 | 11.67 | 21
2 | HOWRAH | Domjur | Howrah Division | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Rudrapur PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000226/2022-2023 | 80/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.29 | 3.29 | 100 | 100
3 | HOWRAH | Domjur | Howrah Division | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Additional carriage of OHR materials & allied works of Rurdrapur PWSS at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000637/2023-2024 | 1239/HD | 12/03/2024 | 26/04/2024 | N. G ENGINEERING | 6.67 | 3.23 | 48.42 | 100
4 | HOWRAH | Domjur | Howrah Division | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Rudrapur PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000665/2022-2023 | 176/HD | 13/01/2023 | 27/02/2023 | DEV DAS SHAW | 37.79 | 37.48 | 99.17 | 100
5 | HOWRAH | Domjur | Howrah Division | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Work Order for Construction for 3(Three) Nos.Pump House (5.40m x 3.60 m), Boundary Wall at Head work Site, 2(Two) nos. Boundary Walls (other sites), Rising Main Pipeline Work & Laying Distribution Pipeline work with Functional Household Tap Connection of Rudrapur PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000772/2022-2023 | 723/HD | 23/02/2023 | 22/08/2023 | PRADIP KUMAR JATI | 290 | 131.63 | 45.39 | 70
6 | HOWRAH | Domjur | Howrah Division | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1748/HD | 25/04/2023 |  | Resource Division | 53.99 | 0 | 0 | 0
7 | HOWRAH | Domjur | Howrah Division | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 135/HD | 10/01/2024 |  | Resource Division | 17.01 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Quotation money deposition for Rudrapur W/S , P.H No-I |  |  | BILL/00733/2023-2024 | 22 | 04/05/2023 |  | WBSEDCL | 0.69 | 0 | 0 | 0
9 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Quotation Bill for New Service Connection at Domjur, Rudrapur W/S. Sch. PH-I |  |  | BILL/00840/2023-2024 | 64 | 08/06/2023 |  | WBSEDCL | 1.86 | 0 | 0 | 0
10 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Deposition of additional quotation money for Rudrapur w/s scheme P.H No.-I ,Dist- Howrah under ED PHED. |  |  | BILL/00968/2023-2024 | null | 07/06/2023 |  | WBSEDCL | 1.86 | 0 | 0 | 0
11 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Adhoc payment to WBSEDCL against service connnection |  |  | BILL/01127/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 109.23 | 0 | 0 | 0
12 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | New service connection for Rudrapur pwss P.H No.-II |  |  | BILL/02569/2023-2024 | 159 | 03/08/2023 |  | WBSEDCL | 3.44 | 0 | 0 | 0
13 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | new service connection for Rudrapur pwss , P.H No.-III |  |  | BILL/02570/2023-2024 | 157 | 03/08/2023 |  | WBSEDCL | 14.97 | 0 | 0 | 0
14 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Quotation Bill for New Service Connection at Rudrapur W/S. Sch. |  |  | BILL/02724/2023-2024 | 168 | 04/08/2023 |  | WBSEDCL | 0.33 | 0 | 0 | 0
15 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Quotation bill for service connection charge for Rudrapur w/s scheme, TW III |  |  | BILL/04433/2023-2024 | 500 | 07/12/2023 |  | WBSEDCL | 11.71 | 0 | 0 | 0
16 | HOWRAH | Domjur | Electrical | Rudrapur PWSS with provision of FHTC connection. | SM/11515 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rudrapur water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000154/2022-2023 | 3519/ED | 30/12/2022 | 30/03/2023 | ORIENTAL ENGINEERING CO. | 34.24 | 0 | 0 | 90
Total | [13 empty] | 734.43 | 192.83 | 26.26