## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta - II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/BLK/amta2,JE/USD | ORD/000238/2023-2024 | 3440/HD | 26/09/2023 | 25/11/2023 | PRANTIK DRILLING AGENCY | 77.89 | 11.76 | 15.1 | 100
2 | HOWRAH | Amta - II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Jagadishpur G.P Area) Zone-14 Length= 536.00mtr.(PART-A) | AE/Ulu | JE/RWS/Amta II | ORD/000246/2020-2021 | 1194/HD | 30/09/2020 | 30/10/2020 | ADITYA HAZRA | 3.12 | 0 | 0 | 0
3 | HOWRAH | Amta - II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Work Order for Preparation of DPR for new piped water supply scheme of Jikira PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/RWS/Amta II | ORD/000441/2021-2022 | 242/HD | 07/02/2022 | 22/02/2022 | VOYAGER | 3.36 | 3.36 | 100 | 0
4 | HOWRAH | Amta - II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation,Construction of Two storied switch room (5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown at Head Work site & 2nd Tube well site, Laying Distribution Pipeline & Providing FHTC (3205 nos) for Jhikira Water Supply Scheme In Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/BLK/amta2 | ORD/000563/2022-2023 | 2501/HD | 30/11/2022 | 29/05/2023 | K.P. CONSTRUCTION | 616.01 | 179.91 | 29.21 | 55
5 | HOWRAH | Amta - II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 1624/HD | 05/08/2022 |  | Resource Division | 21.53 | 0 | 0 | 0
6 | HOWRAH | Amta - II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 170/HD | 15/01/2024 |  | Resource Division | 8.13 | 0 | 0 | 0
7 | HOWRAH | Amta - II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Quotation for Pole Shifting of Jhikira w/s Scheme,PH No-I under Electrical Division,PHE Dte(SM/11719) Application Id-100000105833. Reference Id-860297815. |  |  | BILL/00234/2024-2025 | 84 | 22/04/2024 |  | WBSEDCL | 0.36 | 0 | 0 | null
8 | HOWRAH | Amta - II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Adhoc Payment to WBSEDCL against service Connection |  |  | BILL/01126/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 117.51 | 0 | 0 | 0
9 | HOWRAH | Amta - II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Quotation Bill for New Service Connection at Jhikira W/S. Sch. PH-I |  |  | BILL/04630/2023-2024 | 619 | 08/01/2024 |  | WBSEDCL | 3.86 | 0 | 0 | 0
10 | HOWRAH | Amta - II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Quotation Bill for New Service Connection at Jhikira W/S. Sch. PH-III |  |  | BILL/05720/2023-2024 | 709 | 25/01/2024 |  | WBSEDCL | 12.37 | 0 | 0 | 0
11 | HOWRAH | Amta - II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jhikira water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer5 | ORD/000256/2022-2023 | 923/ED | 22/02/2023 | 23/05/2023 | STANDARD ELECTRICALS | 22.61 | 0 | 0 | 70
Total | [13 empty] | 886.76 | 195.04 | 21.99