## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site of SITAPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS |  | ORD/000037/2024-2025 | 2853/HD | 21/06/2024 | 04/09/2024 | K.N ENTERPRISE | 78.61 | 0 | 0 | 0
2 | HOWRAH | Udaynarayanpur | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sitapur PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000564/2022-2023 | 2548/HD | 02/12/2022 | 16/01/2023 | MUNSHI ENTERPRISE | 36.53 | 15.67 | 42.91 | 90
3 | HOWRAH | Udaynarayanpur | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Sitapur W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000627/2022-2023 | 2808/HD | 21/12/2022 | 19/02/2023 | APEX ENGINEERING | 8.51 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Work order for construction of Pump House ( 5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Sitapur W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000674/2022-2023 | 166/HD | 13/01/2023 | 14/03/2023 | APEX ENGINEERING | 8.52 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1759 nos) for Sitapur PWSS of Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000710/2022-2023 | 380/HD | 01/02/2023 | 31/07/2023 | GUPTA ENTERPRISE | 566.63 | 122.96 | 21.7 | 10
6 | HOWRAH | Udaynarayanpur | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 2830/HD | 04/08/2023 |  | Resource Division | 21.67 | 0 | 0 | 0
7 | HOWRAH | Udaynarayanpur | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 3217/HD | 05/09/2023 |  | Resource Division | 25.95 | 0 | 0 | 0
8 | HOWRAH | Udaynarayanpur | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 421/HD | 03/02/2023 |  | Resource Division | 1.84 | 0 | 0 | 0
9 | HOWRAH | Udaynarayanpur | Electrical | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Adhoc Payment to WBSEDCL against service Connection |  |  | BILL/01126/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 117.51 | 0 | 0 | 0
10 | HOWRAH | Udaynarayanpur | Electrical | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Quotation Bill for New Service Connection at Sitapur W/S. Sch. PH-II |  |  | BILL/04590/2023-2024 | 590 | 29/12/2023 |  | WBSEDCL | 7.22 | 0 | 0 | 0
11 | HOWRAH | Udaynarayanpur | Electrical | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Quotation Bill for New Service Connection at Sitapur W/S. Sch. PH-I |  |  | BILL/04591/2023-2024 | 591 | 29/12/2023 |  | WBSEDCL | 6.37 | 0 | 0 | 0
12 | HOWRAH | Udaynarayanpur | Electrical | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | SM/11853 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sitapur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000160/2022-2023 | 3523/ED | 30/12/2022 | 30/03/2023 | DIPALI CONSTRUCTION | 21.37 | 0 | 0 | 0
Total | [13 empty] | 900.72 | 138.63 | 15.39